## Contracts
Contract ID | Project Name | Client | Start Date | End Date | Value (USD) | Status | Lead Engineer | Section | ProjectManager | ProjectType | LastUpdatedDate
DMS 147714 | ANNUAL REPAIR AND MAINTENANCE OF NAVIGATIONAL BUOYS AND LIGHT POLES | Dubai Holding | 2021-07-01 | 2024-06-30 | 3081439 | CLOSE OUT | ANNEX XAVIER | MARINE INSPECTIONS
DMS 147906 | DESIGN & BUILD CONTRACT FOR BEACH MAINTENANCE WORKS AT PALM JUMEIRAH | Dubai Holding | 2022-09-15 | 2023-12-31 | 116846280.91 | UNDER DNP | MANU REGHURAJAN | MARINE PROJECTS
DMS 148942 | DESIGN REVIEW AND SUPERVISION SERVICES OF BEACH MAINTENANCE WORKS | Dubai Holding | 2024-09-15 | 2023-12-31 | 2026426 | CLOSE OUT | HUSSAIN KHANSAHEB | MARINE PROJECTS
3001-2022-0509 | COMPREHENSIVE CLEANING OF MARINE WASHOUT | Dubai Holding | 2022-12-05 | 2024-02-25 | 3830482 | CLOSED | SAJI HASSAN | MARINE INSPECTIONS
DMS 148857-1 | MARINE CONSULTANCY SERVICES FOR DUBAI ISLANDS A to E | Dubai Holding | 2023-02-17 | 2023-12-10 | 2876809 | ACTIVE | ABDULALEEM HUBOUS | MARINE PROJECTS
3082-2023-0076 | WATER QUALITY TESTING FOR BLUE FLAG CERTIFICATION OF BEACHES | Dubai Holding | 2023-06-01 | 2024-05-31 | 10050 | TERMINATED | ANNEX XAVIER | MARINE PROJECTS
DMS 149323 | CONSULTANCY SERVICES FOR BLUE FLAG CERTIFICATION OF BEACHES IN CONNECTION WITH PALM JUMEIRAH, DUBAI ISLANDS AND DUBAI WATERFRONT | Dubai Holding | 2023-07-20 | 2023-12-19 | 30000 | CLOSED | MANU REGHURAJAN | MARINE PROJECTS
DMS 149250 | CONSULTANCY AGREEMENT FOR ENVIRONMENTAL IMPACT ASSESSMENT SERVICES | Dubai Holding | 2023-08-31 | 2024-06-15 | 1890100 | ACTIVE | HUSSAIN KHANSAHEB | MARINE PROJECTS
3082-2023-0100 | WATER QUALITY TESTING FOR BLUE FLAG CERTIFICATION OF BEACHES | Dubai Holding | 2023-09-11 | - | 20160 | TERMINATED | SAJI HASSAN | MARINE PROJECTS
DMS 149349 | CONSULTANCY AGREEMENT FOR ENVIRONMENTAL IMPACT ASSESSMENT SERVICES | Dubai Holding | - | - | 821600 | ACTIVE | ABDULALEEM HUBOUS | MARINE PROJECTS
3001-2023-0572 | BLUE FLAG CERTIFICATION FOR ALL NAKHEEL BEACHES | Dubai Holding | 2023-12-20 | 2025-12-19 | 154600 | ACTIVE | ANNEX XAVIER | MARINE PROJECTS
3203-2024-0059 | PALM JUMEIRAH BEACHES AND SURFACE WATER CLEANING (AGREEMENT 94478) | Dubai Holding | 2024-03-01 | 2027-02-28 | 8850000 | ACTIVE | MANU REGHURAJAN | MARINE PROJECTS
3082-2024-0024 | COMPREHENSIVE CLEANING OF MARINE WASHOUT ALONG THE MARINE EDGES OF DUBAI ISLANDS A, B, C, D AND E FOR 3 YEARS | Dubai Holding | 2024-04-01 | 2027-03-31 | 1611872.2 | ACTIVE | HUSSAIN KHANSAHEB | MARINE INSPECTIONS
3001-2024-0166 | WATER QUALITY TESTING IN NAKHEEL WATERFRONT PROJECTS | Dubai Holding | 2024-03-05 | 2027-03-04 | 179340 | ACTIVE | SAJI HASSAN | MARINE PROJECTS
DMS 149600 | CONSULTANCY AGREEMENT FOR ENVIRONMENTAL IMPACT ASSESSMENT (EIA) FOR OFFSHORE BORROW AREAS 13 & 14 | Dubai Holding | 2024-03-06 | 2024-05-21 | 548380 | ACTIVE | ABDULALEEM HUBOUS | MARINE PROJECTS
3001-2024-0207 | SUPPLY & INSTALLATION OF NAVIGATION BUOYS AT ALL NAKHEEL WATERFRONT PROJECTS | Dubai Holding | - | - | 5452593 | ACTIVE | ANNEX XAVIER | MARINE INSPECTIONS
3026-2023-0004 | SUPPLY OF UNIFORM FOR NAKHEEL MARINE ENGINEERING | Dubai Holding | - | - | 39370 | CLOSED | MANU REGHURAJAN | MARINE INSPECTIONS
DMS 148763 | MARINE WORKS INCLUDING DREDGING, LAND RECLAMATION AND BEACH PROFILING | Dubai Holding | 2024-09-05 | 2026-11-08 | 918812281.43 | ACTIVE | HUSSAIN KHANSAHEB | MARINE PROJECTS
3026-2024-0001 | SUPPLY OF REMOTELY OPERATED VEHICLES (ROV'S) | Dubai Holding | 2024-02-15 | 2024-03-14 | 662142 | CLOSED | SAJI HASSAN | MARINE INSPECTIONS
3116-2024-0006 | URGENT EMERGENCY WORKS IN THE WORLD - REMOVAL OF CAUSEWAY, CONCRETE DEMOLITION AND DISPOSAL | Dubai Holding | 2024-02-06 | 2024-02-29 | 794178 | CLOSED | ABDULALEEM HUBOUS | MARINE PROJECTS
DMS 149746 | CONSTRUCTION SITE SUPERVISION SERVICES FOR MARINE AND GROUND IMPROVEMENT WORKS | Dubai Holding | 2024-07-12 | 2028-01-11 | 9992685 | ACTIVE | ANNEX XAVIER | MARINE PROJECTS
3051-2023-0077 | WATER QUALITY TESTING FOR BLUE FLAG CERTIFICATION OF BEACHES | Dubai Holding | 2023-12-15 | - | 28350 | CLOSED | MANU REGHURAJAN | MARINE PROJECTS
3082-2023-0099 | WATER QUALITY TESTING WORKS REQUIRED TO SUPPORT THE PREPARATION OF A WATER QUALITY REPORT BY M/S. DOME | Dubai Holding | 2023-09-11 | - | 55450 | CLOSED | HUSSAIN KHANSAHEB | MARINE PROJECTS
DMS 149074 | MARINE IMPACT STUDY CONSULTANCY SERVICES FOR THE PALM JEBEL ALI - FRAMEWORK AGREEMENT | Dubai Holding | 2024-01-29 | 2027-01-08 | 0 | ACTIVE | SAJI HASSAN | MARINE PROJECTS
DMCA-01 | RENEWAL OF SAFE ATONS CERTIFICATE FOR ALL DUBAI HOLDING PROJECTS | Dubai Holding | 2025-01-01 | 2025-12-31 | 400080 | ACTIVE | ABDULALEEM HUBOUS | MARINE INSPECTIONS
DMS 149832 | PALM JEBEL ALI BEACH CLEANING WORKS | Dubai Holding | TBA | TBA | 795756 | ACTIVE | ANNEX XAVIER | MARINE PROJECTS
DMS 149853 | THE POINTE REDEVELOPMENT FOR THE DESIGN & BUILD BEACHES | Dubai Holding | 2025-05-07 | 2025-12-02 | 17245634 | ACTIVE | MANU REGHURAJAN | MARINE PROJECTS

## Activities
Activity ID | Contract ID | Activity Name | Start Date | End Date | Status | Assigned To | Description | CompletionDate | ActivityType | DueDate
1 | DMS 147714 | ,I rue5u | 2024-09-15 | 2024-09-15 | CLOSE OUT | juy ktsr | ,I rue5u | 2024-09-15
2 | DMS 147714 | t hft | 2022-12-05 | 2022-12-05 | UNDER DNP | ht hj | t hft | 2022-12-05
3 | DMCA-01 | j dy | 2023-02-17 | 2023-02-17 | CLOSE OUT | yuk | j dy | 2023-02-17
4 | DMS 149600 | d | 2023-06-01 | 2023-06-01 | CLOSED | jhk | d | 2023-06-01
5 | DMS 149600 | ri6 | 2023-07-20 | 2023-07-20 | ACTIVE | 5ewy54 | ri6 | 2023-07-20
6 | 3082-2023-0076 | ru w | 2023-08-31 | 2023-08-31 | TERMINATED | ui | ru w | 2023-08-31
7 | DMS 149323 | z | 2023-09-01 | 2023-09-01 | CLOSED | ijh | z | 2023-09-01
8 | DMS 149323 | fdyk | 2023-09-02 | 2023-09-02 | ACTIVE | j | fdyk | 2023-09-02
9 | 3116-2024-0006 | t7d | 2023-09-03 | 2023-09-03 | TERMINATED | l | t7d | 2023-09-03
10 | DMS 149349 | ,I rue5u | 2023-09-04 | 2023-09-04 | ACTIVE | juy ktsr | ,I rue5u | 2023-09-04
11 | 3001-2023-0572 | t hft | 2023-09-05 | 2023-09-05 | ACTIVE | ht hj | t hft | 2023-09-05
12 | DMCA-01 | j dy | 2023-09-06 | 2023-09-06 | ACTIVE | yuk | j dy | 2023-09-06
13 | 3116-2024-0006 | d | 2023-09-07 | 2023-09-07 | ACTIVE | jhk | d | 2023-09-07
14 | 3001-2024-0166 | ri6 | 2023-09-08 | 2023-09-08 | ACTIVE | 5ewy54 | ri6 | 2023-09-08
15 | DMS 149600 | ru w | 2023-09-09 | 2023-09-09 | ACTIVE | ui | ru w | 2023-09-09
16 | 3001-2024-0207 | z | 2023-09-10 | 2023-09-10 | ACTIVE | ijh | z | 2023-09-10
17 | 3116-2024-0006 | fdyk | 2024-02-15 | 2024-02-15 | CLOSED | j | fdyk | 2024-02-15
18 | DMS 148763 | PALM JEBEL ALI CONSTRUCTION | 2024-02-06 | 2024-02-06 | ACTIVE | ANNEX XAVIER | PALM JEBEL ALI CONSTRUCTION | 2024-02-06
19 | 3026-2024-0001 | ,I rue5u | 2024-07-12 | 2024-07-12 | CLOSED | juy ktsr | ,I rue5u | 2024-07-12
20 | 3116-2024-0006 | t hft | 2023-12-15 | 2023-12-15 | CLOSED | ht hj | t hft | 2023-12-15
21 | DMS 149746 | j dy | 2023-09-11 | 2023-09-11 | ACTIVE | yuk | j dy | 2023-09-11
22 | 3051-2023-0077 | d | 2024-01-29 | 2024-01-29 | CLOSED | jhk | d | 2024-01-29
23 | DMCA-01 | ri6 | 2025-01-01 | 2025-01-01 | CLOSED | 5ewy54 | ri6 | 2025-01-01
24 | DMS 149074 | ru w | 2025-01-02 | 2025-01-02 | ACTIVE | ui | ru w | 2025-01-02
25 | DMCA-01 | z | 2025-01-03 | 2025-01-03 | ACTIVE | ijh | z | 2025-01-03
26 | DMS 149832 | fdyk | 2025-01-04 | 2025-01-04 | ACTIVE | j | fdyk | 2025-01-04
27 | DMS 149853 | t7d | 2025-01-05 | 2025-01-05 | ACTIVE | l | t7d | 2025-01-05

## Documents
Document ID | Contract ID | Document Name | Document Type | Upload Date | DocumentSubType | DocumentTitle | FileName | FilePathOrURL | UploadDate | Version | AdminNotes | DocumentDate | Tags
ERI1.0 | DMS 148763 | ERI#01 - Additional Sand Stockpiles.pdf | EMPLOYER'S REPRESENTATIVE'S INSTRUCTION |  | ERI # 01.0 | Additional Sand Stockpiles | NKL-LT-12161 - ERI#01 - Additional Sand Stockpiles.pdf | https://dubaiholding-my.sharepoint.com/:b:/r/personal/arun_naidu_dhre_ae/Documents/Documents/NME/MARINE/DMS%20148763%20-%20Marine%20Works%20Including%20Dredging%20and%20Land%20Reclamation%20(Jan%20De%20Nul)/EMPLOYERS%20REPRESENTATIVES%20INSTRUCTION/ERI%2301/NKL-LT-12161%20-%20ERI%2301%20-%20Additional%20Sand%20Stockpiles.pdf?csf=1&web=1&e=7f8NQc | 2025-06-13 | 0
ERI1.1 | DMS 148763 | ERI#01 - Additional Sand Stockpiles.pdf | EMPLOYER'S REPRESENTATIVE'S INSTRUCTION |  | ERI # 01.1 | Additional Sand Stockpiles | NKL-LT-12161 - ERI#01 - Additional Sand Stockpiles.pdf | https://dubaiholding-my.sharepoint.com/:b:/r/personal/arun_naidu_dhre_ae/Documents/Documents/NME/MARINE/DMS%20148763%20-%20Marine%20Works%20Including%20Dredging%20and%20Land%20Reclamation%20(Jan%20De%20Nul)/EMPLOYERS%20REPRESENTATIVES%20INSTRUCTION/ERI%2301/NKL-LT-12161%20-%20ERI%2301%20-%20Additional%20Sand%20Stockpiles.pdf?csf=1&web=1&e=7f8NQc | 2025-06-13 | 1
ERI1.0 | DMCA-01 | ERI#01 - Removal of AtoNs.pdf | EMPLOYER'S REPRESENTATIVE'S INSTRUCTION |  | ERI # 01.0 | Removal of AtoNs | NKL-LT-12161 - ERI#01 - Removal of AtoNs.pdf | https://dubaiholding-my.sharepoint.com/:b:/r/personal/arun_naidu_dhre_ae/Documents/Documents/NME/MARINE/DMS%20148763%20-%20Marine%20Works%20Including%20Dredging%20and%20Land%20Reclamation%20(Jan%20De%20Nul)/EMPLOYERS%20REPRESENTATIVES%20INSTRUCTION/ERI%2301/NKL-LT-12161%20-%20ERI%2301%20-%20Additional%20Sand%20Stockpiles.pdf?csf=1&web=1&e=7f8NQc | 2024-05-12 | 0
ERI1.1 | DMCA-01 | ERI#02 - Removal of AtoNs.pdf | EMPLOYER'S REPRESENTATIVE'S INSTRUCTION |  | ERI # 01.1 | Removal of AtoNs | NKL-LT-12161 - ERI#02 - Removal of AtoNs.pdf | https://dubaiholding-my.sharepoint.com/:b:/r/personal/arun_naidu_dhre_ae/Documents/Documents/NME/MARINE/DMS%20148763%20-%20Marine%20Works%20Including%20Dredging%20and%20Land%20Reclamation%20(Jan%20De%20Nul)/EMPLOYERS%20REPRESENTATIVES%20INSTRUCTION/ERI%2301/NKL-LT-12161%20-%20ERI%2301%20-%20Additional%20Sand%20Stockpiles.pdf?csf=1&web=1&e=7f8NQc | 2024-05-13 | 1
ERI1.2 | DMCA-01 | ERI#03 - Removal of AtoNs.pdf | EMPLOYER'S REPRESENTATIVE'S INSTRUCTION |  | ERI # 01.2 | Removal of AtoNs | NKL-LT-12161 - ERI#03 - Removal of AtoNs.pdf | https://dubaiholding-my.sharepoint.com/:b:/r/personal/arun_naidu_dhre_ae/Documents/Documents/NME/MARINE/DMS%20148763%20-%20Marine%20Works%20Including%20Dredging%20and%20Land%20Reclamation%20(Jan%20De%20Nul)/EMPLOYERS%20REPRESENTATIVES%20INSTRUCTION/ERI%2301/NKL-LT-12161%20-%20ERI%2301%20-%20Additional%20Sand%20Stockpiles.pdf?csf=1&web=1&e=7f8NQc | 2024-05-14 | 2
ERI1.3 | DMCA-01 | ERI#04 - Removal of AtoNs.pdf | EMPLOYER'S REPRESENTATIVE'S INSTRUCTION |  | ERI # 01.3 | Removal of AtoNs | NKL-LT-12161 - ERI#04 - Removal of AtoNs.pdf | https://dubaiholding-my.sharepoint.com/:b:/r/personal/arun_naidu_dhre_ae/Documents/Documents/NME/MARINE/DMS%20148763%20-%20Marine%20Works%20Including%20Dredging%20and%20Land%20Reclamation%20(Jan%20De%20Nul)/EMPLOYERS%20REPRESENTATIVES%20INSTRUCTION/ERI%2301/NKL-LT-12161%20-%20ERI%2301%20-%20Additional%20Sand%20Stockpiles.pdf?csf=1&web=1&e=7f8NQc | 2024-05-15 | 3

## Media
Media ID | Contract ID | File Name | File Type | Upload Date | Description | ImageURL | DateTaken | ActivityID
M00001 | DMS 147714 | FN 1 | JPG | 2025-06-17 | Image 1
M00002 | DMS 147906 | FN 2 | JPG | 2025-06-18 | Image 2
M00003 | DMS 148942 | FN 3 | JPG | 2025-06-19 | Image 3
M00004 | 3001-2022-0509 | FN 4 | JPG | 2025-06-20 | Image 4
M00005 | DMS 148857-1 | FN 5 | JPG | 2025-06-21 | Image 5
M00006 | 3082-2023-0076 | FN 6 | JPG | 2025-06-22 | Image 6
M00007 | DMS 149323 | FN 7 | JPG | 2025-06-23 | Image 7
M00008 | DMS 149250 | FN 8 | JPG | 2025-06-24 | Image 8
M00009 | 3082-2023-0100 | FN 9 | JPG | 2025-06-25 | Image 9
M00010 | DMS 149349 | FN 10 | JPG | 2025-06-26 | Image 10
M00011 | 3001-2023-0572 | FN 11 | JPG | 2025-06-27 | Image 11
M00012 | 3203-2024-0059 | FN 12 | JPG | 2025-06-28 | Image 12
M00013 | 3082-2024-0024 | FN 13 | JPG | 2025-06-29 | Image 13
M00014 | 3001-2024-0166 | FN 14 | JPG | 2025-06-30 | Image 14
M00015 | DMS 149600 | FN 15 | JPG | 2025-07-01 | Image 15
M00016 | 3001-2024-0207 | FN 16 | JPG | 2025-07-02 | Image 16
M00017 | 3026-2023-0004 | FN 17 | JPG | 2025-07-03 | Image 17
M00018 | DMS 148763 | FN 18 | JPG | 2025-07-04 | Image 18
M00019 | 3026-2024-0001 | FN 19 | JPG | 2025-07-05 | Image 19
M00020 | 3116-2024-0006 | FN 20 | JPG | 2025-07-06 | Image 20
M00021 | DMS 149746 | FN 21 | JPG | 2025-07-07 | Image 21
M00022 | 3051-2023-0077 | FN 22 | JPG | 2025-07-08 | Image 22
M00023 | 3082-2023-0099 | FN 23 | JPG | 2025-07-09 | Image 23
M00024 | DMS 149074 | FN 24 | JPG | 2025-07-10 | Image 24
M00025 | DMCA-01 | FN 25 | JPG | 2025-07-11 | Image 25
M00026 | DMS 149832 | FN 26 | JPG | 2025-07-12 | Image 26
M00027 | DMS 149853 | FN 27 | JPG | 2025-07-13 | Image 27