## Contracts
CONTRACT_UID | DEPARTMENT | CLIENT | EMPLOYER | PROJECT_ENTITY | SERVICE_PROVIDER | CONTRACT_REFERENCE | CONTRACT_DESCRIPTION | AGREEMENT_DATE | COMMENCEMENT_DATE | COMPLETION_DATE | REVISED_COMPLETION_DATE | CONT_CONS_CLIE_SUBC | CONTRACT_STATUS | ORIGINAL_CONTRACT_VALUE | APPROVED_VARIATION_AMOUNT | REVISED_CONTRACT_VALUE | APPLICABLE_VAT | VAT_AMOUNT | REVISED_CONTRACT_VALUE_VAT | REMARKS
C00001 | MARINE INSPECTIONS | NAKHEEL PJSC | NAKHEEL PJSC | NAKHEEL WATERFRONT PROJECTS | NORTH WEST MARINE EQUIPMENT TRADING LLC | DMS 147714 | ANNUAL REPAIR AND MAINTENANCE OF NAVIGATIONAL BUOYS AND LIGHT POLES | 2021-06-23 | 2021-07-01 | 2024-06-30 | 2024-06-30 | CONTRACTOR | CLOSE OUT | 3081439 | 0 | 3081439 | YES | 154071.95 | 3235510.95 | -
C00002 | MARINE PROJECTS | NAKHEEL PJSC | COMMUNITYCORP LLC | PALM JUMEIRAH | VAN OORD MIDDLE EAST LIMITED (DUBAI BRANCH) | DMS 147906 | DESIGN & BUILD CONTRACT FOR BEACH MAINTENANCE WORKS AT PALM JUMEIRAH | 2022-09-06 | 2022-09-15 | 2023-09-29 | 2023-12-31 | CONTRACTOR | DEFECTS NOTIFICATION PERIOD | 116726996.19 | 119284.72 | 116846280.91 | YES | 5842314.0455 | 122688594.9555 | -
C00003 | MARINE PROJECTS | NAKHEEL PJSC | COMMUNITYCORP LLC | PALM JUMEIRAH | HALCROW INTERNATIONAL PARTNERSHIP (DUBAI BRANCH) | DMS 148942 | DESIGN REVIEW AND SUPERVISION SERVICES OF BEACH MAINTENANCE WORKS | 2022-10-17 | 2024-09-15 | 2023-10-29 | 2023-12-31 | CONSULTANT | CLOSE OUT | 2026426 | 0 | 2026426 | YES | 101321.3 | 2127747.3 | CLOSE OUT IN PROCESS.
C00004 | MARINE INSPECTIONS | NAKHEEL PJSC | DUBAI ISLANDS LLC | DUBAI ISLANDS | WAAGNER BIRO BRIDGE GULF LLC | 3001-2022-0509 | COMPREHENSIVE CLEANING OF MARINE WASHOUT | 2022-11-23 | 2022-12-05 | 2023-11-04 | 2024-02-25 | CONTRACTOR | CLOSED | 2650000 | 1180482 | 3830482 | YES | 191524.1 | 4022006.1 | CONTRACT EXPIRED. FINAL PAYMENT IN PROCESS.
C00005 | MARINE PROJECTS | NAKHEEL PJSC | DUBAI ISLANDS LLC | DUBAI ISLANDS | MOTT MACDONALD LTD. (DUBAI BRANCH) | DMS 148857-1 | MARINE CONSULTANCY SERVICES FOR DUBAI ISLANDS A to E | 2023-06-02 | 2023-02-17 | 2023-12-10 | 2023-12-10 | CONSULTANT | ACTIVE | 2203598 | 673211 | 2876809 | YES | 143840.45 | 3020649.45 | -
C00006 | MARINE PROJECTS | NAKHEEL PJSC | DUBAI ISLANDS LLC | DUBAI ISLANDS | BUREAU VERITAS (DUBAI BRANCH) | 3082-2023-0076 | WATER QUALITY TESTING FOR BLUE FLAG CERTIFICATION OF BEACHES | 2023-07-13 | 2023-06-01 | 2024-05-31 | 2024-05-31 | CONTRACTOR | TERMINATED | 10050 | 0 | 10050 | YES | 502.5 | 10552.5 | -
C00007 | MARINE PROJECTS | NAKHEEL PJSC | NAKHEEL PJSC | NAKHEEL WATERFRONT PROJECTS | ENVIRO CARE FZE | DMS 149323 | CONSULTANCY SERVICES FOR BLUE FLAG CERTIFICATION OF BEACHES IN CONNECTION WITH PALM JUMEIRAH, DUBAI ISLANDS AND DUBAI WATERFRONT | 2023-07-20 | 2023-07-20 | 2023-12-19 | 2023-12-19 | CONSULTANT | CLOSED | 30000 | 0 | 30000 | NO | 0 | 30000 | CONTRACT IS CLOSED (PO# 3026-2023-0005)
C00008 | MARINE PROJECTS | NAKHEEL PJSC | THE WORLD LLC | THE WORLD ISLANDS AND BORROW AREA | HYDROQUAL ASA | DMS 149250 | CONSULTANCY AGREEMENT FOR ENVIRONMENTAL IMPACT ASSESSMENT SERVICES | 2023-08-31 | 2023-08-31 | 2024-06-15 | 2024-06-15 | CONSULTANT | ACTIVE | 1890100 | 0 | 1890100 | YES | 94505 | 1984605 | -
C00009 | MARINE PROJECTS | NAKHEEL PJSC | DUBAI ISLANDS LLC | DUBAI ISLANDS | BUREAU VERITAS (DUBAI BRANCH) | 3082-2023-0100 | WATER QUALITY TESTING FOR BLUE FLAG CERTIFICATION OF BEACHES | 2023-09-11 | 2023-09-11 | - | - | CONTRACTOR | TERMINATED | 20160 | 0 | 20160 | YES | 1008 | 21168 | -
C00010 | MARINE PROJECTS | NAKHEEL PJSC | DUBAI ISLANDS LLC | DUBAI ISLANDS | BUREAU VERITAS (DUBAI BRANCH) | 3082-2023-0099 | WATER QUALITY TESTING WORKS REQUIRED TO SUPPORT THE PREPARATION OF A WATER QUALITY REPORT BY M/S. DOME | 2023-09-11 | 2023-09-11 | - | - | CONTRACTOR | CLOSED | 55450 | 0 | 55450 | YES | 2772.5 | 58222.5 | -
C00011 | MARINE PROJECTS | NAKHEEL PJSC | DUBAI WATERFRONT LLC | DUBAI WATERFRONT | DOME INTERNATIONAL SAFETY AND ENVIRONMENTAL CONSULTANTS | DMS 149349 | CONSULTANCY AGREEMENT FOR ENVIRONMENTAL IMPACT ASSESSMENT SERVICES | 2023-11-23 | - | - | - | CONSULTANT | ACTIVE | 821600 | 0 | 821600 | YES | 41080 | 862680 | -
C00012 | MARINE PROJECTS | NAKHEEL PJSC | THE PALM JEBEL ALI CO. LLC | PALM JEBEL ALI | BUREAU VERITAS (DUBAI BRANCH) | 3051-2023-0077 | WATER QUALITY TESTING FOR BLUE FLAG CERTIFICATION OF BEACHES | 2023-12-15 | 2023-12-15 | - | - | CONTRACTOR | CLOSED | 28350 | 0 | 28350 | YES | 1417.5 | 29767.5 | -
C00013 | MARINE PROJECTS | NAKHEEL PJSC | NAKHEEL PJSC | NAKHEEL WATERFRONT PROJECTS | ENVIRO CARE FZE | 3001-2023-0572 | BLUE FLAG CERTIFICATION FOR ALL NAKHEEL BEACHES | 2023-12-20 | 2023-12-20 | 2025-12-19 | 2025-12-19 | CONSULTANT | ACTIVE | 154600 | 0 | 154600 | YES | 7730 | 162330 | -
C00014 | MARINE PROJECTS | DUBAI HOLDING REAL ESTATE | THE PALM JEBEL ALI CO. LLC | PALM JEBEL ALI | HALCROW INTERNATIONAL PARTNERSHIP (DUBAI BRANCH) | DMS 149074 | MARINE IMPACT STUDY CONSULTANCY SERVICES FOR THE PALM JEBEL ALI - FRAMEWORK AGREEMENT | 2024-01-29 | 2024-01-29 | 2027-01-28 | 2027-01-08 | CONSULTANT | ACTIVE | 0 | 0 | 0 | YES | 0 | 0 | -
C00015 | MARINE PROJECTS | NAKHEEL PJSC | THE WORLD LLC | THE WORLD ISLANDS | PLC MARINE TRANSPORT LLC | 3116-2024-0006 | URGENT EMERGENCY WORKS IN THE WORLD - REMOVAL OF CAUSEWAY, CONCRETE DEMOLITION AND DISPOSAL | 2024-02-07 | 2024-02-06 | 2024-02-29 | 2024-02-29 | CONTRACTOR | CLOSED | 794178 | 0 | 794178 | YES | 39708.9 | 833886.9 | -
C00016 | MARINE INSPECTIONS | NAKHEEL PJSC | NAKHEEL PJSC | NAKHEEL WATERFRONT PROJECTS | INCHCAPE SHIPPING SERVICES (DUBAI) LLC | 3026-2024-0001 | SUPPLY OF REMOTELY OPERATED VEHICLES (ROV'S) | 2024-02-15 | 2024-02-15 | 2024-03-14 | 2024-03-14 | SUPPLIER | CLOSED | 662142 | 0 | 662142 | YES | 33107.1 | 695249.1 | -
C00017 | MARINE PROJECTS | NAKHEEL PJSC | COMMUNITYCORP LLC | PALM JUMEIRAH | IMDAAD LLC | 3203-2024-0059 | PALM JUMEIRAH BEACHES AND SURFACE WATER CLEANING (AGREEMENT 94478) | 2024-02-21 | 2024-03-01 | 2027-02-28 | 2027-02-28 | CONTRACTOR | ACTIVE | 8850000 | 0 | 8850000 | YES | 442500 | 9292500 | -
C00018 | MARINE INSPECTIONS | NAKHEEL PJSC | DUBAI ISLANDS LLC | DUBAI ISLANDS | IFM FACILITIES MANAGEMENT LLC | 3082-2024-0024 | COMPREHENSIVE CLEANING OF MARINE WASHOUT ALONG THE MARINE EDGES OF DUBAI ISLANDS A, B, C, D AND E FOR 3 YEARS | 2024-02-22 | 2024-04-01 | 2027-03-31 | 2027-03-31 | CONTRACTOR | ACTIVE | 1611872.2 | 0 | 1611872.2 | YES | 80593.61 | 1692465.81 | -
C00019 | MARINE PROJECTS | NAKHEEL PJSC | NAKHEEL PJSC | NAKHEEL WATERFRONT PROJECTS | WAFA BIOLOGICAL LABORATORY LLC | 3001-2024-0166 | WATER QUALITY TESTING IN NAKHEEL WATERFRONT PROJECTS | 2024-03-04 | 2024-03-05 | 2027-03-04 | 2027-03-04 | CONTRACTOR | ACTIVE | 179340 | 0 | 179340 | YES | 8967 | 188307 | -
C00020 | MARINE PROJECTS | NAKHEEL PJSC | DUBAI ISLANDS LLC | DUBAI ISLANDS | DOME INTERNATIONAL SAFETY AND ENVIRONMENTAL CONSULTANTS | DMS 149600 | CONSULTANCY AGREEMENT FOR ENVIRONMENTAL IMPACT ASSESSMENT (EIA) FOR OFFSHORE BORROW AREAS 13 & 14 | 2024-03-06 | 2024-03-06 | 2024-05-21 | 2024-05-21 | CONSULTANT | ACTIVE | 548380 | 0 | 548380 | YES | 27419 | 575799 | -
C00021 | MARINE INSPECTIONS | NAKHEEL PJSC | NAKHEEL PJSC | NAKHEEL WATERFRONT PROJECTS | NORTH WEST MARINE EQUIPMENT TRADING LLC | 3001-2024-0207 | SUPPLY & INSTALLATION OF NAVIGATION BUOYS AT ALL NAKHEEL WATERFRONT PROJECTS | 2024-03-21 | - | - | - | CONTRACTOR | ACTIVE | 5452593 | 0 | 5452593 | YES | 272629.65 | 5725222.65 | - AGREEMENT 96435 - CONTRACT NOT YET SIGNED. 2nd SIGNATORY UNDECIDED. THE MAINTENANCE PERIOD WILL START AFTER COMPLETION OF INSTALLATION OF ALL BUOYS.
C00022 | MARINE PROJECTS | DUBAI HOLDING REAL ESTATE | THE PALM JEBEL ALI CO. LLC | PALM JEBEL ALI | HALCROW INTERNATIONAL PARTNERSHIP (DUBAI BRANCH) | DMS 149746 | CONSTRUCTION SITE SUPERVISION SERVICES FOR MARINE AND GROUND IMPROVEMENT WORKS | 2024-08-21 | 2024-07-12 | 2028-01-11 | 2028-01-11 | CONSULTANT | ACTIVE | 9992685 | 0 | 9992685 | YES | 499634.25 | 10492319.25 | -
C00023 | MARINE PROJECTS | DUBAI HOLDING REAL ESTATE | THE PALM JEBEL ALI CO. LLC | PALM JEBEL ALI | JAN DE NUL DREDGING LTD. (DUBAI BRANCH) | DMS 148763 | MARINE WORKS INCLUDING DREDGING, LAND RECLAMATION AND BEACH PROFILING | 2024-08-23 | 2024-09-05 | 2026-11-08 | 2026-11-08 | CONTRACTOR | ACTIVE | 810529166.67 | 108283114.76 | 918812281.43 | YES | 45940614.0715 | 964752895.5015 | -
C00024 | MARINE PROJECTS | DUBAI HOLDING REAL ESTATE | THE POINTE LLC | PALM JUMEIRAH | VAN OORD MIDDLE EAST LIMITED (DUBAI BRANCH) | DMS 149853 | THE POINTE REDEVELOPMENT FOR THE DESIGN & BUILD BEACHES | 2025-04-07 | 2025-05-07 | 2025-12-02 | 2025-12-02 | CONTRACTOR | ACTIVE | 17245634 | 0 | 17245634 | YES | 862281.7 | 18107915.7 | -
C00025 | MARINE INSPECTIONS | DUBAI HOLDING REAL ESTATE | NAKHEEL PJSC | NAKHEEL WATERFRONT PROJECTS | DUBAI MARITIME CITY AUTHORITY | DMCA-01 | RENEWAL OF SAFE ATONS CERTIFICATE FOR ALL DUBAI HOLDING PROJECTS | - | 2025-01-01 | 2025-12-31 | 2025-12-31 | AUTHORITY | ACTIVE | 400080 | 0 | 400080 | NO | 0 | 400080 | NO CONTRACT AGREEMENT IS AVAILABLE FOR THIS. IT IS A YEARLY FEE PAID TO DMCA AUTHORITY.
C00026 | MARINE INSPECTIONS | NAKHEEL PJSC | NAKHEEL PJSC | NAKHEEL MARINE ENGINEERING | ROOH AL MASHRIQ FASHION | 3026-2023-0004 | SUPPLY OF UNIFORM FOR NAKHEEL MARINE ENGINEERING | - | - | - | - | SUPPLIER | CLOSED | 39370 | 0 | 39370 | YES | 1968.5 | 41338.5 | AWAITING RECEIPT OF FINAL INVOICE
C00027 | MARINE INSPECTIONS | DUBAI HOLDING REAL ESTATE | THE PALM JEBEL ALI CO. LLC | PALM JEBEL ALI | IMDAAD LLC | DMS 149832 | PALM JEBEL ALI BEACH CLEANING WORKS | TBA | TBA | TBA | TBA | CONTRACTOR | ACTIVE | 795756 | 0 | 795756 | YES | 39787.8 | 835543.8 | CONTRACT TO BE FINALIZED BY P&C
Formulas:
REVISED_COMPLETION_DATE = IF([COMPLETION_DATE]="","",[COMPLETION_DATE])
REVISED_COMPLETION_DATE = [COMPLETION_DATE]
COMPLETION_DATE = [COMMENCEMENT_DATE]+77-1

## Activities (hidden)
Activity ID | Contract ID | Activity Name | Start Date | End Date | Status | Assigned To | Description | CompletionDate | ActivityType | DueDate
1 | DMS 147714 | ,I rue5u | 2024-09-15 | 2024-09-15 | CLOSE OUT | juy ktsr | ,I rue5u | 2024-09-15
2 | DMS 147714 | t hft | 2022-12-05 | 2022-12-05 | UNDER DNP | ht hj | t hft | 2022-12-05
3 | DMCA-01 | j dy | 2023-02-17 | 2023-02-17 | CLOSE OUT | yuk | j dy | 2023-02-17
4 | DMS 149600 | d | 2023-06-01 | 2023-06-01 | CLOSED | jhk | d | 2023-06-01
5 | DMS 149600 | ri6 | 2023-07-20 | 2023-07-20 | ACTIVE | 5ewy54 | ri6 | 2023-07-20
6 | 3082-2023-0076 | ru w | 2023-08-31 | 2023-08-31 | TERMINATED | ui | ru w | 2023-08-31
7 | DMS 149323 | z | 2023-09-01 | 2023-09-01 | CLOSED | ijh | z | 2023-09-01
8 | DMS 149323 | fdyk | 2023-09-02 | 2023-09-02 | ACTIVE | j | fdyk | 2023-09-02
9 | 3116-2024-0006 | t7d | 2023-09-03 | 2023-09-03 | TERMINATED | l | t7d | 2023-09-03
10 | DMS 149349 | ,I rue5u | 2023-09-04 | 2023-09-04 | ACTIVE | juy ktsr | ,I rue5u | 2023-09-04
11 | 3001-2023-0572 | t hft | 2023-09-05 | 2023-09-05 | PENDING | ht hj | t hft | 2023-09-05
12 | DMCA-01 | j dy | 2023-09-06 | 2023-09-06 | ACTIVE | yuk | j dy | 2023-09-06
13 | 3116-2024-0006 | d | 2023-09-07 | 2023-09-07 | ACTIVE | jhk | d | 2023-09-07
14 | 3001-2024-0166 | ri6 | 2023-09-08 | 2023-09-08 | ACTIVE | 5ewy54 | ri6 | 2023-09-08
15 | DMS 149600 | ru w | 2023-09-09 | 2023-09-09 | PENDING | ui | ru w | 2023-09-09
16 | 3001-2024-0207 | z | 2023-09-10 | 2023-09-10 | ACTIVE | ijh | z | 2023-09-10
17 | 3116-2024-0006 | fdyk | 2024-02-15 | 2024-02-15 | CLOSED | j | fdyk | 2024-02-15
18 | DMS 148763 | PALM JEBEL ALI CONSTRUCTION | 2024-02-06 | 2024-02-06 | ACTIVE | ANNEX XAVIER | PALM JEBEL ALI CONSTRUCTION | 2024-02-06
19 | 3026-2024-0001 | ,I rue5u | 2024-07-12 | 2024-07-12 | PENDING | juy ktsr | ,I rue5u | 2024-07-12
20 | 3116-2024-0006 | t hft | 2023-12-15 | 2023-12-15 | CLOSED | ht hj | t hft | 2023-12-15
21 | DMS 149746 | j dy | 2023-09-11 | 2023-09-11 | ACTIVE | yuk | j dy | 2023-09-11
22 | 3051-2023-0077 | d | 2024-01-29 | 2024-01-29 | CLOSED | jhk | d | 2024-01-29
23 | DMCA-01 | ri6 | 2025-01-01 | 2025-01-01 | CLOSED | 5ewy54 | ri6 | 2025-01-01
24 | DMS 149074 | ru w | 2025-01-02 | 2025-01-02 | ACTIVE | ui | ru w | 2025-01-02
25 | DMCA-01 | z | 2025-01-03 | 2025-01-03 | PENDING | ijh | z | 2025-01-03
26 | DMS 149832 | fdyk | 2025-01-04 | 2025-01-04 | ACTIVE | j | fdyk | 2025-01-04
27 | DMS 149853 | t7d | 2025-01-05 | 2025-01-05 | ACTIVE | l | t7d | 2025-01-05

## Documents (hidden)
Document ID | Contract ID | Document Name | Document Type | Upload Date | DocumentSubType | DocumentTitle | FileName | FilePathOrURL | UploadDate | Version | AdminNotes | DocumentDate | Tags
ERI1.0 | DMS 148763 | ERI#01 - Additional Sand Stockpiles.pdf | EMPLOYER'S REPRESENTATIVE'S INSTRUCTION |  | ERI # 01.0 | Additional Sand Stockpiles | NKL-LT-12161 - ERI#01 - Additional Sand Stockpiles.pdf | https://dubaiholding-my.sharepoint.com/:b:/r/personal/arun_naidu_dhre_ae/Documents/Documents/NME/MARINE/DMS%20148763%20-%20Marine%20Works%20Including%20Dredging%20and%20Land%20Reclamation%20(Jan%20De%20Nul)/EMPLOYERS%20REPRESENTATIVES%20INSTRUCTION/ERI%2301/NKL-LT-12161%20-%20ERI%2301%20-%20Additional%20Sand%20Stockpiles.pdf?csf=1&web=1&e=7f8NQc | 2025-06-13 | 0
ERI1.1 | DMS 148763 | ERI#01 - Additional Sand Stockpiles.pdf | EMPLOYER'S REPRESENTATIVE'S INSTRUCTION |  | ERI # 01.1 | Additional Sand Stockpiles | NKL-LT-12161 - ERI#01 - Additional Sand Stockpiles.pdf | Z:\USERS\Concept design and Options Report_rev2_25.7 Including Appendices.pdf | 2025-06-13 | 1
ERI1.0 | DMCA-01 | ERI#01 - Removal of AtoNs.pdf | EMPLOYER'S REPRESENTATIVE'S INSTRUCTION |  | ERI # 01.0 | Removal of AtoNs | NKL-LT-12161 - ERI#01 - Removal of AtoNs.pdf | https://dubaiholding-my.sharepoint.com/:b:/r/personal/arun_naidu_dhre_ae/Documents/Documents/NME/MARINE/DMS%20148763%20-%20Marine%20Works%20Including%20Dredging%20and%20Land%20Reclamation%20(Jan%20De%20Nul)/EMPLOYERS%20REPRESENTATIVES%20INSTRUCTION/ERI%2301/NKL-LT-12161%20-%20ERI%2301%20-%20Additional%20Sand%20Stockpiles.pdf?csf=1&web=1&e=7f8NQc | 2024-05-12 | 0
ERI1.1 | DMCA-01 | ERI#02 - Removal of AtoNs.pdf | EMPLOYER'S REPRESENTATIVE'S INSTRUCTION |  | ERI # 01.1 | Removal of AtoNs | NKL-LT-12161 - ERI#02 - Removal of AtoNs.pdf | https://dubaiholding-my.sharepoint.com/:b:/r/personal/arun_naidu_dhre_ae/Documents/Documents/NME/MARINE/DMS%20148763%20-%20Marine%20Works%20Including%20Dredging%20and%20Land%20Reclamation%20(Jan%20De%20Nul)/EMPLOYERS%20REPRESENTATIVES%20INSTRUCTION/ERI%2301/NKL-LT-12161%20-%20ERI%2301%20-%20Additional%20Sand%20Stockpiles.pdf?csf=1&web=1&e=7f8NQc | 2024-05-13 | 1
ERI1.2 | DMCA-01 | ERI#03 - Removal of AtoNs.pdf | EMPLOYER'S REPRESENTATIVE'S INSTRUCTION |  | ERI # 01.2 | Removal of AtoNs | NKL-LT-12161 - ERI#03 - Removal of AtoNs.pdf | Z:\USERS\Concept design and Options Report_rev2_25.7 Including Appendices.pdf | 2024-05-14 | 2
ERI1.3 | DMCA-01 | ERI#04 - Removal of AtoNs.pdf | EMPLOYER'S REPRESENTATIVE'S INSTRUCTION |  | ERI # 01.3 | Removal of AtoNs | NKL-LT-12161 - ERI#04 - Removal of AtoNs.pdf | https://dubaiholding-my.sharepoint.com/personal/arun_naidu_dhre_ae/Documents/Shared/ME/assets/DMS%20149250/PC/PC-04.pdf | 2024-05-15 | 3
PC1.0 | DMS 149600 | PC#01 - Payment Certificate.pdf | PAYMENT CERTIFICATE | 2025-06-19 | PC # 01.0 | Payment Certificate # 01 | PC-01.PDF | https://dubaiholding-my.sharepoint.com/:b:/g/personal/arun_naidu_dhre_ae/EUysg7T3ajdIsj6J81h2b_8BqMv40tjbbnmHigxS5cyl8w?email=Arun.Naidu%40dhre.ae&e=fNZcxb | 2025-06-19 | 0
PC2.0 | DMS 149600 | PC#02 - Payment Certificate.pdf | PAYMENT CERTIFICATE | 2025-06-20 | PC # 02.0 | Payment Certificate # 02 | PC-02.PDF | https://dubaiholding-my.sharepoint.com/:b:/g/personal/arun_naidu_dhre_ae/EUysg7T3ajdIsj6J81h2b_8BqMv40tjbbnmHigxS5cyl8w?email=Arun.Naidu%40dhre.ae&e=fNZcxb | 2025-06-20 | 0
PC9.0 | DMS 148857-1 | PC#09 - Payment Certificate.pdf | PAYMENT CERTIFICATE | 2025-06-21 | PC # 09.0 | Payment Certificate # 09 | PC-09.PDF | https://dubaiholding-my.sharepoint.com/personal/arun_naidu_dhre_ae/Documents/Shared/ME/assets/DMS%20148857-1/PC/PC-09.pdf | 2025-06-21 | 0
PC10.0 | DMS 148857-1 | PC#10 - Payment Certificate.pdf | PAYMENT CERTIFICATE | 2025-06-22 | PC # 10.0 | Payment Certificate # 10 | PC-10.PDF | https://dubaiholding-my.sharepoint.com/personal/arun_naidu_dhre_ae/Documents/Shared/ME/assets/DMS%20148857-1/PC/PC-10.pdf | 2025-06-22 | 0

## Media (hidden)
Media ID | ContractID | File Name | File Type | Upload Date | Description | ImageURL | DateTaken | ActivityID | WeekNumber
M00001 | DMS 147714 | FN 1 | JPG | 2025-06-17 | Image 1 | https://raw.githubusercontent.com/Excalibur1902/me_dashboard/photos/DMS%20147906/Week1/20190616_192611.jpg |  |  | Week
M00002 | DMS 147906 | FN 2 | JPG | 2025-06-18 | Image 2 | https://raw.githubusercontent.com/Excalibur1902/me_dashboard/photos/DMS%20147906/Week1/20221008_190132.jpg
M00003 | DMS 148763 | FN 3 | JPG | 2025-06-19 | Image 3 | https://raw.githubusercontent.com/Excalibur1902/me_dashboard/photos/DMS%20147906/Week1/20221008_190132.jpg
M00004 | DMS 148763 | FN 4 | JPG | 2025-06-20 | Image 4 | https://raw.githubusercontent.com/Excalibur1902/me_dashboard/photos/DMS%20147906/Week1/20221008_190132.jpg
M00005 | DMS 147906 | FN 5 | JPG | 2025-06-21 | Image 5 | https://raw.githubusercontent.com/Excalibur1902/me_dashboard/photos/DMS%20147906/Week1/20221008_190132.jpg
M00006 | 3082-2023-0076 | FN 6 | JPG | 2025-06-22 | Image 6 | https://raw.githubusercontent.com/Excalibur1902/me_dashboard/photos/DMS%20147906/Week1/20221008_190132.jpg
M00007 | DMS 149323 | FN 7 | JPG | 2025-06-23 | Image 7 | https://raw.githubusercontent.com/Excalibur1902/me_dashboard/photos/DMS%20147906/Week1/20221008_190132.jpg
M00008 | DMS 148763 | FN 8 | JPG | 2025-06-24 | Image 8 | https://raw.githubusercontent.com/Excalibur1902/me_dashboard/photos/DMS%20147906/Week1/20221008_190132.jpg
M00009 | 3082-2023-0100 | FN 9 | JPG | 2025-06-25 | Image 9 | https://raw.githubusercontent.com/Excalibur1902/me_dashboard/photos/DMS%20147906/Week1/20221008_190132.jpg
M00010 | DMS 149349 | FN 10 | JPG | 2025-06-26 | Image 10 | https://raw.githubusercontent.com/Excalibur1902/me_dashboard/photos/DMS%20147906/Week1/20221008_190132.jpg
M00011 | DMS 147906 | FN 11 | JPG | 2025-06-27 | Image 11 | https://raw.githubusercontent.com/Excalibur1902/me_dashboard/photos/DMS%20147906/Week1/20221008_190132.jpg
M00012 | 3203-2024-0059 | FN 12 | JPG | 2025-06-28 | Image 12 | https://raw.githubusercontent.com/Excalibur1902/me_dashboard/photos/DMS%20147906/Week1/20221008_190132.jpg
M00013 | DMS 148763 | FN 13 | JPG | 2025-06-29 | Image 13 | https://raw.githubusercontent.com/Excalibur1902/me_dashboard/photos/DMS%20147906/Week1/20221008_190132.jpg
M00014 | 3001-2024-0166 | FN 14 | JPG | 2025-06-30 | Image 14 | https://raw.githubusercontent.com/Excalibur1902/me_dashboard/photos/DMS%20147906/Week1/20221008_190132.jpg
M00015 | DMS 149600 | FN 15 | JPG | 2025-07-01 | Image 15 | https://raw.githubusercontent.com/Excalibur1902/me_dashboard/photos/DMS%20147906/Week1/20221008_190132.jpg
M00016 | 3001-2024-0207 | FN 16 | JPG | 2025-07-02 | Image 16 | https://raw.githubusercontent.com/Excalibur1902/me_dashboard/photos/DMS%20147906/Week1/20221008_190132.jpg
M00017 | DMS 147906 | FN 17 | JPG | 2025-07-03 | Image 17 | https://raw.githubusercontent.com/Excalibur1902/me_dashboard/photos/DMS%20147906/Week1/20221008_190132.jpg
M00018 | DMS 148763 | FN 18 | JPG | 2025-07-04 | Image 18 | https://raw.githubusercontent.com/Excalibur1902/me_dashboard/photos/DMS%20147906/Week1/20221008_190132.jpg
M00019 | 3026-2024-0001 | FN 19 | JPG | 2025-07-05 | Image 19 | https://raw.githubusercontent.com/Excalibur1902/me_dashboard/photos/DMS%20147906/Week1/20221008_190132.jpg
M00020 | 3116-2024-0006 | FN 20 | JPG | 2025-07-06 | Image 20 | https://raw.githubusercontent.com/Excalibur1902/me_dashboard/photos/DMS%20147906/Week1/20221008_190132.jpg
M00021 | DMS 149746 | FN 21 | JPG | 2025-07-07 | Image 21 | https://raw.githubusercontent.com/Excalibur1902/me_dashboard/photos/DMS%20147906/Week1/20221008_190132.jpg
M00022 | DMS 147906 | FN 22 | JPG | 2025-07-08 | Image 22 | https://raw.githubusercontent.com/Excalibur1902/me_dashboard/photos/DMS%20147906/Week1/20221008_190132.jpg
M00023 | 3082-2023-0099 | FN 23 | JPG | 2025-07-09 | Image 23 | https://raw.githubusercontent.com/Excalibur1902/me_dashboard/photos/DMS%20147906/Week1/20221008_190132.jpg
M00024 | DMS 149074 | FN 24 | JPG | 2025-07-10 | Image 24 | https://raw.githubusercontent.com/Excalibur1902/me_dashboard/photos/DMS%20147906/Week1/20221008_190132.jpg
M00025 | DMCA-01 | FN 25 | JPG | 2025-07-11 | Image 25 | https://raw.githubusercontent.com/Excalibur1902/me_dashboard/photos/DMS%20147906/Week1/20221008_190132.jpg
M00026 | DMS 148763 | FN 26 | JPG | 2025-07-12 | Image 26 | https://raw.githubusercontent.com/Excalibur1902/me_dashboard/photos/DMS%20147906/Week1/20221008_190132.jpg
M00027 | DMS 148763 | FN 27 | JPG | 2025-07-13 | Image 27 | https://raw.githubusercontent.com/Excalibur1902/me_dashboard/photos/DMS%20147906/Week1/20221008_190132.jpg

## Payments
CONTRACT_UID | PC_NO: | PC_REVISION | PC_DATE: | PC TYPE: | DUE DATE: | STATUS: | PC AMOUNT: | PC AMOUNT + VAT: | DMS REFERENCE: | REMARKS:
C00001 | 1 | 0 | 2021-08-17 | INTERIM | 2021-09-26 | CERTIFIED | 102105 | 107210.25 | 0113-0821-0008 | PAYMENT RECEIVED - CONFIRMED BY DUNCAN VIA E-MAIL ON 30/03/2023.
C00001 | 2 | 0 | 2021-09-15 | INTERIM | 2021-10-25 | CERTIFIED | 29705 | 31190.25 | 0113-0921-0009
C00001 | 3 | 0 | 2022-02-03 | INTERIM | 2022-03-17 | CERTIFIED | 1245605 | 1307885.25 | 0113-0222-0001
C00001 | 4 | 0 | 2022-03-16 | INTERIM | 2022-04-24 | CERTIFIED | 134334 | 141050.7 | 0113-0322-0008 | PAID - AS CONFIRMED BY IQBAL VIA TEAMS ON 31/03/2022.
C00001 | 5 | 0 | 2022-05-12 | INTERIM | 2022-06-14 | CERTIFIED | 76300 | 80115 | 0113-0522-0006 | PAID - AS CONFIRMED BY IQBAL VERBALLY ON 30/05/2022.
C00001 | 6 | 0 | 2022-06-14 | INTERIM | 2022-07-21 | CERTIFIED | 67247.2 | 70609.56 | 0112-0622-0008 | PAYMENT MADE ON 15/07/2022
C00001 | 7 | 0 | 2022-08-30 | INTERIM | 2022-10-11 | CERTIFIED | 121215 | 127275.75 | 0113-0822-0012 | PAID - PAYMENT ADVISE PROVIDED BY NAVEED ON 25/10/2022
C00001 | 8 | 0 | 2022-11-17 | INTERIM | 2023-01-01 | CERTIFIED | 121815 | 127905.75 | 0113-1122-0005
C00001 | 9 | 0 | 2022-12-20 | INTERIM | 2023-01-31 | CERTIFIED | 35970 | 37768.5 | 0113-1222-0002
C00001 | 10 | 0 | 2023-02-02 | INTERIM | 2023-03-08 | CERTIFIED | 109050 | 114502.5 | 0113-0223-0002
C00001 | 11 | 0 | 2023-03-02 | INTERIM | 2023-04-10 | CERTIFIED | 33665 | 35348.25 | 0113-0323-0005
C00001 | 12 | 0 | 2023-04-04 | INTERIM | 2023-05-23 | CERTIFIED | 59949 | 62946.45 | 0113-0423-0005
C00001 | 13 | 0 | 2023-05-08 | INTERIM | 2023-06-26 | CERTIFIED | 96333 | 101149.65 | 0113-0523-0008
C00001 | 14 | 0 | 2023-06-12 | INTERIM | 2023-07-31 | CERTIFIED | 34927 | 36673.35 | 0113-0623-0034
C00001 | 15 | 0 | 2023-07-06 | INTERIM | 2023-08-24 | CERTIFIED | 24187 | 25396.35 | 0113-0723-0004
C00001 | 16 | 0 | 2023-08-04 | INTERIM | 2023-09-22 | CERTIFIED | 95618 | 100398.9 | 0113-0823-0012
C00001 | 17 | 0 | 2023-09-13 | INTERIM | 2023-11-01 | CERTIFIED | 24187 | 25396.35 | 0113-0923-0009
C00001 | 18 | 0 | 2023-10-05 | INTERIM | 2023-11-23 | CERTIFIED | 24187 | 25396.35 | 0113-1023-0005
C00001 | 19 | 0 | 2023-11-10 | INTERIM | 2023-12-29 | CERTIFIED | 170453 | 178975.65 | 0113-1123-0010
C00001 | 20 | 0 | 2023-12-11 | INTERIM | 2024-01-29 | CERTIFIED | 36552 | 38379.6 | 0113-1223-0003
C00001 | 21 | 0 | 2024-01-15 | INTERIM | 2024-03-04 | CERTIFIED | 25396.35 | 26666.1675 | 0113-0124-0008
C00001 | 22 | 0 | 2024-02-09 | INTERIM | 2024-03-26 | CERTIFIED | 92763 | 97401.15 | 0113-0224-0014
C00001 | 23 | 0 | 2024-03-11 | INTERIM | 2024-04-29 | CERTIFIED | 25087 | 26341.35 | 0
C00001 | 24 | 0 | 2024-04-26 | INTERIM | 2024-06-14 | CERTIFIED | 43597 | 45776.85 | 0
C00001 | 25 | 0 | 2024-06-28 | INTERIM | 2024-08-16 | CERTIFIED | 141509 | 148584.45 | 0
C00001 | 26 | 0 | 2024-08-06 | INTERIM | 2024-09-24 | CERTIFIED | 28687 | 30121.35 | PC-26
C00002 | 1 | 0 | 2022-10-11 | ADVANCE PAYMENT | 2022-10-23 | CERTIFIED | 11672699.62 | 12256334.601 | 0
C00002 | 1 | 0 | 2023-11-16 | INTERIM | 2023-12-31 | CERTIFIED | 5849473.5 | 6141947.175 | 0113-1123-0014 / 0113-0224-0018 | ERI # 04 - PALM BEACH TOWER: BEACH AND GROYNE WORKS (NAKHEEL DEVELOPMENT)
C00002 | 2 | 0 | 2025-04-09 | FINAL | 2025-05-24 | CERTIFIED | 649941.5 | 682438.575 | PC-02 | PALM BEACH TOWER
C00002 | 1 | 0 | 2023-12-06 | INTERIM | 2024-01-20 | CERTIFIED | 1665000 | 1748250 | 0113-1223-0011 / 0113-0224-0019 | ERI # 09 - SAND SEARCH OFFSHORE DUBAI BY SUB-BOTTOM PROFILE AND VIBRO CORE METHOD (NAKHEEL DEVELOPMENT)
C00002 | 2 | 0 | 2025-04-09 | FINAL | 2025-05-24 | CERTIFIED | 185000 | 194250 | PC-02 | SAND SEARCH
C00002 | 2 | 0 | 2022-11-11 | INTERIM | 2022-12-15 | CERTIFIED | 1843013.4 | 1935164.07 | 0113-1122-0006
C00002 | 3 | 0 | 2022-05-04 | INTERIM | 2023-06-18 | CERTIFIED | 2143102.45 | 2250257.5725 | 0113-0523-0010
C00002 | 4 | 0 | 2023-05-31 | INTERIM | 2023-06-20 | CERTIFIED | 7521150.23 | 7897207.7415 | 0
C00002 | 5 | 0 | 2023-06-14 | INTERIM | 2023-07-18 | CERTIFIED | 3016237.19 | 3167049.0495 | 0
C00002 | 6 | 0 | 2023-07-26 | INTERIM | 2023-08-18 | CERTIFIED | 17237850.5 | 18099743.025 | 0113-0823-0001
C00002 | 7 | 0 | 2023-08-02 | INTERIM | 2023-09-16 | CERTIFIED | 13940523.55 | 14637549.7275 | 0113-0823-0019
C00002 | 8 | 0 | 2023-09-01 | INTERIM | 2023-10-16 | CERTIFIED | 19360569.28 | 20328597.744 | 0113-0923-0017
C00002 | 9 | 0 | 2023-10-02 | INTERIM | 2023-11-16 | CERTIFIED | 15182740.87 | 15941877.9135 | 0113-1023-0016
C00002 | 10 | 0 | 2023-11-02 | INTERIM | 2023-12-17 | CERTIFIED | 14119966.81 | 14825965.1505 | 0113-1123-0013
C00002 | 11 | 0 | 2023-12-01 | INTERIM | 2024-01-15 | CERTIFIED | 8363439.9 | 8781611.895 | 0113-1223-0015
C00002 | 12 | 0 | 2024-06-26 | STATEMENT AT COMPLETION | 2024-08-10 | VOIDED | 2121807.34 | 2227897.707 | PC-12 | * ON HOLD AS PER HAF INSTRUCTION. * THE INVOICE WAS REVISED AND REISSUED BY VAN OORD. THIS REVISED INVOICE IS PROCESSED UNDER PC#12A.
C00002 | 12 | 1 | 2025-04-09 | FINAL | 2025-05-02 | CERTIFIED | 2444987.13 | 2567236.4865 | PC-12A | * SENT VIA EMAIL TO DOCUMENT MANAGEMENT FOR FURTHER CIRCULATION TO DHCM OPERATIONS TEAM.
C00003 | 1 | 0 | 2022-12-20 | INTERIM | 2023-01-27 | CERTIFIED | 116569 | 122397.45 | 0113-0123-0006 | PAYMENT RECEIVED - CONFIRMED BY DUNCAN VIA E-MAIL ON 30/03/2023.
C00003 | 2 | 0 | 2023-07-13 | INTERIM | 2023-08-26 | CERTIFIED | 271348.39 | 284915.8095 | 0
C00003 | 3 | 0 | 2023-07-20 | INTERIM | 2023-08-19 | CERTIFIED | 120100 | 126105 | 0113-0823-0006
C00003 | 4 | 0 | 2023-08-10 | INTERIM | 2023-09-09 | CERTIFIED | 123212 | 129372.6 | 0113-0823-0018
C00003 | 5 | 0 | 2023-09-11 | INTERIM | 2023-10-11 | CERTIFIED | 122052.31 | 128154.9255 | 0113-0923-0015
C00003 | 6 | 0 | 2023-10-13 | INTERIM | 2023-11-12 | CERTIFIED | 127826.5 | 134217.825 | 0113-1023-0015
C00003 | 7 | 0 | 2023-11-15 | INTERIM | 2023-12-15 | CERTIFIED | 118900 | 124845 | 0113-1123-0012
C00003 | 8 | 0 | 2023-12-21 | INTERIM | 2024-01-20 | CERTIFIED | 111723.55 | 117309.7275 | 0113-0124-0002
C00003 | 9 | 0 | 2024-02-01 | INTERIM | 2024-03-02 | CERTIFIED | 70637.5 | 74169.375 | PC-09
C00003 | 10 | 0 | 2024-05-17 | INTERIM | 2024-06-16 | CERTIFIED | 38857 | 40799.85 | PC-10
C00003 | 11 | 0 | 2024-07-24 | INTERIM | 2024-08-23 | CERTIFIED | 26355 | 27672.75 | PC-11
C00003 | 12 | 0 | 2025-04-11 | INTERIM | 2025-05-11 | CERTIFIED | 96115.38 | 100921.149 | PC-12
C00005 | 1 | 0 | 2023-05-21 | INTERIM | 2023-06-20 | CERTIFIED | 220359.8 | 231377.79 | 0113-0623-0026
C00005 | 2 | 0 | 2023-05-21 | INTERIM | 2023-06-20 | CERTIFIED | 115946.11 | 121743.4155 | 0113-0623-0027
C00005 | 3 | 0 | 2023-06-30 | INTERIM | 2023-08-10 | CERTIFIED | 28986.51 | 30435.8355 | 0113-0823-0014 | PAID ON 17/08/2023
C00005 | 4 | 0 | 2023-09-18 | INTERIM | 2023-10-18 | CERTIFIED | 279218.16 | 293179.068 | 0113-1023-0009
C00005 | 5 | 0 | 2023-09-18 | INTERIM | 2023-10-18 | CERTIFIED | 327777.84 | 344166.732 | 0113-1023-0008
C00005 | 6 | 0 | 2024-01-30 | INTERIM | 2024-02-29 | CERTIFIED | 80000 | 84000 | 0113-0224-0017 | PAID
C00005 | 7 | 0 | 2024-03-10 | INTERIM | 2024-04-09 | CERTIFIED | 369000 | 387450 | 0113-0324-0005 | PAID
C00005 | 8 | 0 | 2024-04-25 | INTERIM | 2024-05-25 | CERTIFIED | 35910 | 37705.5 | 0
C00005 | 9 | 0 | 2024-06-16 | INTERIM | 2024-07-16 | CERTIFIED | 567479.45 | 595853.4225 | PC-09
C00005 | 10 | 0 | 2024-08-01 | INTERIM | 2024-08-31 | CERTIFIED | 636580.46 | 668409.483 | PC-10
C00006 | 1 | 0 | 2023-10-17 | INTERIM | ASAP | CERTIFIED | 4580 | 4809 | RFP-01
C00006 | 2 | 0 | 2023-12-15 | INTERIM | ASAP | CERTIFIED | 1300 | 1365 | RFP-02
C00006 | 3 | 0 | 2024-02-05 | INTERIM | ASAP | CERTIFIED | 650 | 682.5 | RFP-03
C00006 | 4 | 0 | 2024-03-12 | INTERIM | ASAP | CERTIFIED | 650 | 682.5 | RFP-04
C00006 | 5 | 0 | 2024-06-07 | INTERIM | ASAP | CERTIFIED | 650 | 682.5 | RFP-05
C00008 | 1 | 0 | 2023-12-11 | INTERIM | 2024-01-13 | CERTIFIED | 334600 | 351330 | 0113-1223-0004
C00008 | 2 | 0 | 2024-01-15 | INTERIM | 2024-02-19 | CERTIFIED | 1206420 | 1266741 | 0113-0124-0006
C00008 | 3 | 0 | 2024-05-13 | INTERIM | 2024-06-27 | CERTIFIED | 195120 | 204876 | PC-03
C00008 | 4 | 0 | 2024-11-07 | INTERIM | 2024-12-22 | CERTIFIED | 153960 | 161658 | PC-04
C00009 | 1 | 0 | 2023-10-17 | INTERIM | ASAP | CERTIFIED | 4800 | 5040 | RFP-01
C00009 | 2 | 0 | 2023-12-15 | INTERIM | ASAP | CERTIFIED | 3840 | 4032 | RFP-02
C00009 | 3 | 0 | 2024-02-05 | INTERIM | ASAP | CERTIFIED | 1920 | 2016 | RFP-03
C00009 | 4 | 0 | 2024-03-12 | INTERIM | ASAP | CERTIFIED | 1920 | 2016 | RFP-04
C00009 | 5 | 0 | 2024-06-07 | INTERIM | ASAP | CERTIFIED | 1920 | 2016 | RFP-05
C00011 | 1 | 0 | 2023-10-04 | INTERIM | 2023-11-30 | CERTIFIED | 205400 | 215670 | 0113-1023-0017
C00011 | 2 | 0 | 2024-02-09 | INTERIM | 2024-03-22 | CERTIFIED | 451880 | 474474 | 0113-0224-0015
C00013 | 1 | 0 | 2024-02-06 | INTERIM | ASAP | CERTIFIED | 29600 | 29600 | RFP-01
C00013 | 2 | 0 | 2024-03-12 | INTERIM | ASAP | CERTIFIED | 12920 | 12920 | RFP-02
C00013 | 3 | 0 | 2024-05-24 | INTERIM | ASAP | CERTIFIED | 10260 | 10260 | RFP-03
C00013 | 4 | 0 | 2024-08-07 | INTERIM | ASAP | CERTIFIED | 27170 | 27170 | RFP-04
C00013 | 5 | 0 | 2024-08-14 | INTERIM | ASAP | CERTIFIED | 2660 | 2660 | RFP-05
C00013 | 6 | 0 | 2024-10-24 | INTERIM | ASAP | CERTIFIED | 19570 | 19570 | RFP-06 | Entry made on 28/10/2024
C00013 | 7 | 0 | 2024-12-12 | INTERIM | ASAP | CERTIFIED | 29060 | 29060 | RFP-07 | Entry made on 20/12/2024
C00013 | 8 | 0 | 2024-12-12 | INTERIM | ASAP | CERTIFIED | 2660 | 2660 | RFP-08 | Entry made on 19/12/2024
C00017 | 1 | 0 | 2024-10-28 | INTERIM | 2024-12-16 | PENDING | 1606458.26 | 1686781.173 | PC-01 | CERTIFIED BUT PAYMENT IS NOT RELEASED.
C00017 | 2 | 0 | 2024-11-25 | INTERIM | 2025-01-13 | PENDING | 231249.99 | 242812.4895 | PC-02 | CERTIFIED BUT PAYMENT IS NOT RELEASED.
C00017 | 3 | 0 | 2024-12-17 | INTERIM | 2025-02-04 | PENDING | 231249.99 | 242812.4895 | PC-03
C00018 | 1 | 0 | 2024-06-27 | INTERIM | 2024-08-26 | CERTIFIED | 89548.46 | 94025.883 | PC-01
C00018 | 2 | 0 | 2024-09-30 | INTERIM | 2024-11-29 | CERTIFIED | 134322.69 | 141038.8245 | PC-02 | Updated on 09/10/24
C00018 | 3 | 0 | 2024-12-16 | INTERIM | 2025-02-14 | CERTIFIED | 134322.69 | 141038.8245 | PC-03 | Updated on 07/01/25
C00018 | 4 | 0 | 2025-01-16 | INTERIM | 2025-05-17 | CERTIFIED | 44774.23 | 47012.9415 | PC-04 | Updated on 29/01/25
C00019 | 1 | 0 | 2024-04-29 | INTERIM | ASAP | CERTIFIED | 891 | 935.55 | RFP-01
C00019 | 2 | 0 | 2024-06-21 | INTERIM | ASAP | CERTIFIED | 891 | 935.55 | RFP-02
C00019 | 3 | 0 | 2024-08-26 | INTERIM | ASAP | CERTIFIED | 891 | 935.55 | RFP-03
C00019 | 4 | 0 | 2024-09-17 | INTERIM | ASAP | CERTIFIED | 3267 | 3430.35 | RFP-04
C00019 | 5 | 0 | 2025-02-20 | INTERIM | ASAP | CERTIFIED | 6831 | 7172.55 | RFP-05
C00020 | 1 | 0 | 2024-07-23 | INTERIM | 2024-08-25 | CERTIFIED | 493542 | 518219.1 | PC-01
C00021 | 1 | 0 | 2024-09-17 | INTERIM | 2024-11-05 | CERTIFIED | 3936989.39 | 4133838.8595 | PC-01
C00023 | 1 | 0 | 2024-10-02 | ADVANCE PAYMENT | 2024-11-01 | CERTIFIED | 81052916.67 | 85105562.5035 | PC-01
C00023 | 2 | 0 | 2024-10-18 | INTERIM | 2024-12-17 | CERTIFIED | 29857679.2 | 31350563.16 | PC-02
C00023 | 3 | 0 | 2024-11-19 | INTERIM | 2025-01-18 | CERTIFIED | 43555004.74 | 45732754.977 | PC-03
C00023 | 4 | 0 | 2024-12-18 | INTERIM | 2025-02-16 | CERTIFIED | 36820924.51 | 38661970.7355 | PC-04
C00023 | 5 | 0 | 2025-02-04 | INTERIM | 2025-03-11 | CERTIFIED | 37643805.5 | 39525995.775 | PC-05
C00023 | 6 | 0 | 2025-04-09 | INTERIM | 2025-05-11 | CERTIFIED | 87629153.7 | 92010611.385 | PC-06
C00023 | 7 | 0 | 2025-04-16 | INTERIM | 2025-05-20 | CERTIFIED | 39918957.34 | 41914905.207 | PC-07
C00023 | 8 | 0 | 2025-05-05 | INTERIM | 2025-06-14 | CERTIFIED | 22445684.66 | 23567968.893 | PC-08
C00023 | 9 | 0 | 2025-05-21 | INTERIM | 2025-07-14 | CERTIFIED | 30214778.63 | 31725517.5615 | PC-09
C00022 | 1 | 0 | 2024-11-13 | INTERIM | 2024-12-13 | CERTIFIED | 480204.79 | 504215.0295 | PC-01
C00022 | 2 | 0 | 2024-12-29 | INTERIM | 2025-01-28 | CERTIFIED | 674118.61 | 707824.5405 | PC-02
C00022 | 3 | 0 | 2025-01-24 | INTERIM | 2025-02-21 | CERTIFIED | 378676.98 | 397610.829 | PC-03
C00012 | 1 | 0 | 2023-12-15 | FINAL | 2024-01-14 | CERTIFIED | 28350 | 29767.5 | RFP-01
C00010 | 1 | 0 | 2023-09-12 | FINAL | ASAP | CERTIFIED | 55450 | 58222.5 | RFP-01
C00025 | 1 | 0 | 2025-01-03 | FINAL | 2025-02-17 | CERTIFIED | 400080 | 400080 | RFP-01

## Securities
CONTRACT_UID | GUARANTEE_TYPE | GUARANTEE_MODE | BANK | GUARANTEE_REFERENCE | GUARANTEE_VALUE | GUARANTEE_VALIDITY
C00001 | PERFORMANCE | SECURITY CHEQUE | COMMERCIAL BANK OF DUBAI | 005511:402320117:1000652428 | 154071.95 | UNDATED
C00002 | PERFORMANCE | BANK GUARANTEE | BNP PARIBAS | 06685IGD2200438 | 11672699.62 | END OF DLP
C00003 | N/A | N/A | N/A | N/A | N/A | N/A
C00004 | N/A | N/A | N/A | N/A | N/A | N/A
C00005 | N/A | N/A | N/A | N/A | N/A | N/A
C00006 | N/A | N/A | N/A | N/A | N/A | N/A
C00007 | N/A | N/A | N/A | N/A | N/A | N/A
C00008 | N/A | N/A | N/A | N/A | N/A | N/A
C00009 | N/A | N/A | N/A | N/A | N/A | N/A
C00010 | N/A | N/A | N/A | N/A | N/A | N/A
C00011 | N/A | N/A | N/A | N/A | N/A | N/A
C00012 | N/A | N/A | N/A | N/A | N/A | N/A
C00013 | N/A | N/A | N/A | N/A | N/A | N/A
C00014 | N/A | N/A | N/A | N/A | N/A | N/A
C00015 | N/A | N/A | N/A | N/A | N/A | N/A
C00016 | N/A | N/A | N/A | N/A | N/A | N/A
C00017 | N/A | N/A | N/A | N/A | N/A | N/A
C00018 | N/A | N/A | N/A | N/A | N/A | N/A
C00019 | N/A | N/A | N/A | N/A | N/A | N/A
C00020 | N/A | N/A | N/A | N/A | N/A | N/A
C00021 | PERFORMANCE | BANK GUARANTEE | COMMERCIAL BANK OF DUBAI | OLG2401469-17 | 234728 | 2027-06-19
C00022 | N/A | N/A | N/A | N/A | N/A | N/A
C00023 | N/A | N/A | N/A | N/A | N/A | N/A
C00024 | N/A | N/A | N/A | N/A | N/A | N/A
C00025 | N/A | N/A | N/A | N/A | N/A | N/A
C00026 | N/A | N/A | N/A | N/A | N/A | N/A
C00027 | N/A | N/A | N/A | N/A | N/A | N/A
C00001 | N/A | N/A | N/A | N/A | N/A | N/A
C00002 | ADVANCE | BANK GUARANTEE | BNP PARIBAS | 06685IGD2200434 | 8151662.88 | UNTIL NOTIFIED
C00003 | N/A | N/A | N/A | N/A | N/A | N/A
C00004 | N/A | N/A | N/A | N/A | N/A | N/A
C00005 | N/A | N/A | N/A | N/A | N/A | N/A
C00006 | N/A | N/A | N/A | N/A | N/A | N/A
C00007 | N/A | N/A | N/A | N/A | N/A | N/A
C00008 | N/A | N/A | N/A | N/A | N/A | N/A
C00009 | N/A | N/A | N/A | N/A | N/A | N/A
C00010 | N/A | N/A | N/A | N/A | N/A | N/A
C00011 | N/A | N/A | N/A | N/A | N/A | N/A
C00012 | N/A | N/A | N/A | N/A | N/A | N/A
C00013 | N/A | N/A | N/A | N/A | N/A | N/A
C00014 | N/A | N/A | N/A | N/A | N/A | N/A
C00015 | N/A | N/A | N/A | N/A | N/A | N/A
C00016 | N/A | N/A | N/A | N/A | N/A | N/A
C00017 | N/A | N/A | N/A | N/A | N/A | N/A
C00018 | N/A | N/A | N/A | N/A | N/A | N/A
C00019 | N/A | N/A | N/A | N/A | N/A | N/A
C00020 | N/A | N/A | N/A | N/A | N/A | N/A
C00021 | N/A | N/A | N/A | N/A | N/A | N/A
C00022 | N/A | N/A | N/A | N/A | N/A | N/A
C00023 | N/A | N/A | N/A | N/A | N/A | N/A
C00024 | N/A | N/A | N/A | N/A | N/A | N/A
C00025 | N/A | N/A | N/A | N/A | N/A | N/A
C00026 | N/A | N/A | N/A | N/A | N/A | N/A
C00027 | N/A | N/A | N/A | N/A | N/A | N/A
C00001 | N/A | N/A | N/A | N/A | N/A | N/A
C00002 | RETENTION | BANK GUARANTEE | BNP PARIBAS | 06685IGD2200434 | 8151662.88 | UNTIL NOTIFIED
C00003 | N/A | N/A | N/A | N/A | N/A | N/A
C00004 | N/A | N/A | N/A | N/A | N/A | N/A
C00005 | N/A | N/A | N/A | N/A | N/A | N/A
C00006 | N/A | N/A | N/A | N/A | N/A | N/A
C00007 | N/A | N/A | N/A | N/A | N/A | N/A
C00008 | N/A | N/A | N/A | N/A | N/A | N/A
C00009 | N/A | N/A | N/A | N/A | N/A | N/A
C00010 | N/A | N/A | N/A | N/A | N/A | N/A
C00011 | N/A | N/A | N/A | N/A | N/A | N/A
C00012 | N/A | N/A | N/A | N/A | N/A | N/A
C00013 | N/A | N/A | N/A | N/A | N/A | N/A
C00014 | N/A | N/A | N/A | N/A | N/A | N/A
C00015 | N/A | N/A | N/A | N/A | N/A | N/A
C00016 | N/A | N/A | N/A | N/A | N/A | N/A
C00017 | N/A | N/A | N/A | N/A | N/A | N/A
C00018 | N/A | N/A | N/A | N/A | N/A | N/A
C00019 | N/A | N/A | N/A | N/A | N/A | N/A
C00020 | N/A | N/A | N/A | N/A | N/A | N/A
C00021 | N/A | N/A | N/A | N/A | N/A | N/A
C00022 | N/A | N/A | N/A | N/A | N/A | N/A
C00023 | N/A | N/A | N/A | N/A | N/A | N/A
C00024 | N/A | N/A | N/A | N/A | N/A | N/A
C00025 | N/A | N/A | N/A | N/A | N/A | N/A
C00026 | N/A | N/A | N/A | N/A | N/A | N/A
C00027 | N/A | N/A | N/A | N/A | N/A | N/A

## Insurances
CONTRACT_UID | INSURANCE_TYPE | INSURED | INSURER | INSURANCE_REFERENCE | INSURED_VALUE | VALIDITY
C00001 | CAR AND TPL | N/A | N/A | N/A | N/A | N/A
C00002 | CAR AND TPL | VAN OORD MIDDLE EAST LTD | ORIENT INSURANCE PJSC | P/01/4012/2022/93 | 124000000 | 2023-12-31
C00003 | CAR AND TPL | N/A | N/A | N/A | N/A | N/A
C00004 | CAR AND TPL | N/A | N/A | N/A | N/A | N/A
C00005 | CAR AND TPL | N/A | N/A | N/A | N/A | N/A
C00006 | CAR AND TPL | N/A | N/A | N/A | N/A | N/A
C00007 | CAR AND TPL | N/A | N/A | N/A | N/A | N/A
C00008 | CAR AND TPL | N/A | N/A | N/A | N/A | N/A
C00009 | CAR AND TPL | N/A | N/A | N/A | N/A | N/A
C00010 | CAR AND TPL | N/A | N/A | N/A | N/A | N/A
C00011 | CAR AND TPL | N/A | N/A | N/A | N/A | N/A
C00012 | CAR AND TPL | N/A | N/A | N/A | N/A | N/A
C00013 | CAR AND TPL | N/A | N/A | N/A | N/A | N/A
C00014 | CAR AND TPL | N/A | N/A | N/A | N/A | N/A
C00015 | CAR AND TPL | N/A | N/A | N/A | N/A | N/A
C00016 | CAR AND TPL | N/A | N/A | N/A | N/A | N/A
C00017 | CAR AND TPL | N/A | N/A | N/A | N/A | N/A
C00018 | CAR AND TPL | N/A | N/A | N/A | N/A | N/A
C00019 | CAR AND TPL | N/A | N/A | N/A | N/A | N/A
C00020 | CAR AND TPL | N/A | N/A | N/A | N/A | N/A
C00021 | CAR AND TPL | N/A | N/A | N/A | N/A | N/A
C00022 | CAR AND TPL | N/A | N/A | N/A | N/A | N/A
C00023 | CAR AND TPL | N/A | N/A | N/A | N/A | N/A
C00024 | CAR AND TPL | N/A | N/A | N/A | N/A | N/A
C00025 | CAR AND TPL | N/A | N/A | N/A | N/A | N/A
C00026 | CAR AND TPL | N/A | N/A | N/A | N/A | N/A
C00027 | CAR AND TPL | N/A | N/A | N/A | N/A | N/A
C00001 | WORKMEN COMPENSATION INSURANCE | N/A | N/A | N/A | N/A | N/A
C00002 | WORKMEN COMPENSATION INSURANCE | N/A | N/A | N/A | N/A | N/A
C00003 | WORKMEN COMPENSATION INSURANCE | N/A | N/A | N/A | N/A | N/A
C00004 | WORKMEN COMPENSATION INSURANCE | N/A | N/A | N/A | N/A | N/A
C00005 | WORKMEN COMPENSATION INSURANCE | N/A | N/A | N/A | N/A | N/A
C00006 | WORKMEN COMPENSATION INSURANCE | N/A | N/A | N/A | N/A | N/A
C00007 | WORKMEN COMPENSATION INSURANCE | N/A | N/A | N/A | N/A | N/A
C00008 | WORKMEN COMPENSATION INSURANCE | N/A | N/A | N/A | N/A | N/A
C00009 | WORKMEN COMPENSATION INSURANCE | N/A | N/A | N/A | N/A | N/A
C00010 | WORKMEN COMPENSATION INSURANCE | N/A | N/A | N/A | N/A | N/A
C00011 | WORKMEN COMPENSATION INSURANCE | N/A | N/A | N/A | N/A | N/A
C00012 | WORKMEN COMPENSATION INSURANCE | N/A | N/A | N/A | N/A | N/A
C00013 | WORKMEN COMPENSATION INSURANCE | N/A | N/A | N/A | N/A | N/A
C00014 | WORKMEN COMPENSATION INSURANCE | N/A | N/A | N/A | N/A | N/A
C00015 | WORKMEN COMPENSATION INSURANCE | N/A | N/A | N/A | N/A | N/A
C00016 | WORKMEN COMPENSATION INSURANCE | N/A | N/A | N/A | N/A | N/A
C00017 | WORKMEN COMPENSATION INSURANCE | N/A | N/A | N/A | N/A | N/A
C00018 | WORKMEN COMPENSATION INSURANCE | N/A | N/A | N/A | N/A | N/A
C00019 | WORKMEN COMPENSATION INSURANCE | N/A | N/A | N/A | N/A | N/A
C00020 | WORKMEN COMPENSATION INSURANCE | N/A | N/A | N/A | N/A | N/A
C00021 | WORKMEN COMPENSATION INSURANCE | N/A | N/A | N/A | N/A | N/A
C00022 | WORKMEN COMPENSATION INSURANCE | N/A | N/A | N/A | N/A | N/A
C00023 | WORKMEN COMPENSATION INSURANCE | N/A | N/A | N/A | N/A | N/A
C00024 | WORKMEN COMPENSATION INSURANCE | N/A | N/A | N/A | N/A | N/A
C00025 | WORKMEN COMPENSATION INSURANCE | N/A | N/A | N/A | N/A | N/A
C00026 | WORKMEN COMPENSATION INSURANCE | N/A | N/A | N/A | N/A | N/A
C00027 | WORKMEN COMPENSATION INSURANCE | N/A | N/A | N/A | N/A | N/A
C00001 | PLANT & EQUIPMENT INSURANCE | N/A | N/A | N/A | N/A | N/A
C00002 | PLANT & EQUIPMENT INSURANCE | N/A | N/A | N/A | N/A | N/A
C00003 | PLANT & EQUIPMENT INSURANCE | N/A | N/A | N/A | N/A | N/A
C00004 | PLANT & EQUIPMENT INSURANCE | N/A | N/A | N/A | N/A | N/A
C00005 | PLANT & EQUIPMENT INSURANCE | N/A | N/A | N/A | N/A | N/A
C00006 | PLANT & EQUIPMENT INSURANCE | N/A | N/A | N/A | N/A | N/A
C00007 | PLANT & EQUIPMENT INSURANCE | N/A | N/A | N/A | N/A | N/A
C00008 | PLANT & EQUIPMENT INSURANCE | N/A | N/A | N/A | N/A | N/A
C00009 | PLANT & EQUIPMENT INSURANCE | N/A | N/A | N/A | N/A | N/A
C00010 | PLANT & EQUIPMENT INSURANCE | N/A | N/A | N/A | N/A | N/A
C00011 | PLANT & EQUIPMENT INSURANCE | N/A | N/A | N/A | N/A | N/A
C00012 | PLANT & EQUIPMENT INSURANCE | N/A | N/A | N/A | N/A | N/A
C00013 | PLANT & EQUIPMENT INSURANCE | N/A | N/A | N/A | N/A | N/A
C00014 | PLANT & EQUIPMENT INSURANCE | N/A | N/A | N/A | N/A | N/A
C00015 | PLANT & EQUIPMENT INSURANCE | N/A | N/A | N/A | N/A | N/A
C00016 | PLANT & EQUIPMENT INSURANCE | N/A | N/A | N/A | N/A | N/A
C00017 | PLANT & EQUIPMENT INSURANCE | N/A | N/A | N/A | N/A | N/A
C00018 | PLANT & EQUIPMENT INSURANCE | N/A | N/A | N/A | N/A | N/A
C00019 | PLANT & EQUIPMENT INSURANCE | N/A | N/A | N/A | N/A | N/A
C00020 | PLANT & EQUIPMENT INSURANCE | N/A | N/A | N/A | N/A | N/A
C00021 | PLANT & EQUIPMENT INSURANCE | N/A | N/A | N/A | N/A | N/A
C00022 | PLANT & EQUIPMENT INSURANCE | N/A | N/A | N/A | N/A | N/A
C00023 | PLANT & EQUIPMENT INSURANCE | N/A | N/A | N/A | N/A | N/A
C00024 | PLANT & EQUIPMENT INSURANCE | N/A | N/A | N/A | N/A | N/A
C00025 | PLANT & EQUIPMENT INSURANCE | N/A | N/A | N/A | N/A | N/A
C00026 | PLANT & EQUIPMENT INSURANCE | N/A | N/A | N/A | N/A | N/A
C00027 | PLANT & EQUIPMENT INSURANCE | N/A | N/A | N/A | N/A | N/A
C00001 | PROFESSIONAL INDEMNITY | N/A | N/A | N/A | N/A | N/A
C00002 | PROFESSIONAL INDEMNITY | N/A | N/A | N/A | N/A | N/A
C00003 | PROFESSIONAL INDEMNITY | CH2M HILL INTERNATIONAL, LTD. - DUBAI BRANCH (CHIL-DUBAI) | EMIRATES INSURANCE | 906/1165/90/21/00005/02 | 10000000 | 2024-07-01
C00004 | PROFESSIONAL INDEMNITY | N/A | N/A | N/A | N/A | N/A
C00005 | PROFESSIONAL INDEMNITY | MOTT MACDONALD LIMITED | EMIRATES INSURANCE | 908/1165/90/20/00015/03 | 10000000 | 2024-06-30
C00006 | PROFESSIONAL INDEMNITY | N/A | N/A | N/A | N/A | N/A
C00007 | PROFESSIONAL INDEMNITY | N/A | N/A | N/A | N/A | N/A
C00008 | PROFESSIONAL INDEMNITY | HYDROQUAL ASA | ORIENT INSURANCE PJSC | P/01/6023/2023/156 | 3672500 | 2024-05-31
C00009 | PROFESSIONAL INDEMNITY | N/A | N/A | N/A | N/A | N/A
C00010 | PROFESSIONAL INDEMNITY | N/A | N/A | N/A | N/A | N/A
C00011 | PROFESSIONAL INDEMNITY | DOME INTERNATIONAL SAFETY AND ENVIRONMENTAL CONSULTANTS | ABU DHABI NATIONAL INSURANCE COMPANY | H155130047709-R06 | 18350000 | 2024-11-30
C00012 | PROFESSIONAL INDEMNITY | N/A | N/A | N/A | N/A | N/A
C00013 | PROFESSIONAL INDEMNITY | N/A | N/A | N/A | N/A | N/A
C00014 | PROFESSIONAL INDEMNITY | N/A | N/A | N/A | N/A | N/A
C00015 | PROFESSIONAL INDEMNITY | N/A | N/A | N/A | N/A | N/A
C00016 | PROFESSIONAL INDEMNITY | N/A | N/A | N/A | N/A | N/A
C00017 | PROFESSIONAL INDEMNITY | N/A | N/A | N/A | N/A | N/A
C00018 | PROFESSIONAL INDEMNITY | N/A | N/A | N/A | N/A | N/A
C00019 | PROFESSIONAL INDEMNITY | N/A | N/A | N/A | N/A | N/A
C00020 | PROFESSIONAL INDEMNITY | DOME INTERNATIONAL SAFETY AND ENVIRONMENTAL CONSULTANTS | ABU DHABI NATIONAL INSURANCE COMPANY | H155130047709-R06 | 18350000 | 2024-11-30
C00021 | PROFESSIONAL INDEMNITY | N/A | N/A | N/A | N/A | N/A
C00022 | PROFESSIONAL INDEMNITY | N/A | N/A | N/A | N/A | N/A
C00023 | PROFESSIONAL INDEMNITY | N/A | N/A | N/A | N/A | N/A
C00024 | PROFESSIONAL INDEMNITY | N/A | N/A | N/A | N/A | N/A
C00025 | PROFESSIONAL INDEMNITY | N/A | N/A | N/A | N/A | N/A
C00026 | PROFESSIONAL INDEMNITY | N/A | N/A | N/A | N/A | N/A
C00027 | PROFESSIONAL INDEMNITY | N/A | N/A | N/A | N/A | N/A

## MASTER (hidden)
MASTER SL. # | DEPARTMENT | DEPT. SL. # | COMPANY | EMPLOYER | ENTITY (PROJECT) | SERVICE PROVIDER | CONTRACT REFERENCE | CONTRACT DESCRIPTION | AGREEMENT DATE | COMMENCEMENT DATE | COMPLETION DATE | REVISED COMPLETION DATE | CONTRACTOR / CONSULTANT / CLIENT | STATUS | ORIGINAL CONTRACT VALUE | APPROVED VARIATION AMOUNT | REVISED CONTRACT VALUE | IS VAT APPLICABLE? (YES OR NO) | VAT | REVISED CONTRACT VALUE + VAT | REMARKS | LATEST CERTIFIED PC # | DATED | PC TYPE | DUE DATE | STATUS | PC AMOUNT | PC AMOUNT + VAT | BANK GUARANTEE / SECURITY CHEQUE | BANK DETAILS | REF. # | AMOUNT | VALIDITY | BANK GUARANTEE / SECURITY CHEQUE | BANK DETAILS | REF. # | AMOUNT | VALIDITY | BANK GUARANTEE / SECURITY CHEQUE | BANK DETAILS | REF. # | AMOUNT | VALIDITY | INSURANCE PROCURED BY | INSURER | REF. # | AMOUNT | VALIDITY | INSURANCE PROCURED BY | INSURER | REF. # | AMOUNT | VALIDITY | INSURANCE PROCURED BY | INSURER | REF. # | AMOUNT | VALIDITY | INSURANCE PROCURED BY | INSURER | REF. # | AMOUNT | VALIDITY
1 | MARINE INSPECTIONS | 1 | NAKHEEL PJSC | NAKHEEL PJSC | NAKHEEL WATERFRONT PROJECTS | NORTH WEST MARINE EQUIPMENT TRADING LLC | DMS 147714 | ANNUAL REPAIR AND MAINTENANCE OF NAVIGATIONAL BUOYS AND LIGHT POLES | 2021-06-23 | 2021-07-01 | 2024-06-30 | 2024-06-30 | CONTRACTOR | CLOSE OUT | 3081439 | 0 | 3081439 | YES | 154071.95 | 3235510.95 | - | 26 | 2024-08-06 | INTERIM | 2024-09-24 | CERTIFIED | 28687 | 30121.35 | SECURITY CHEQUE | COMMERCIAL BANK OF DUBAI | 005511:402320117:1000652428 | 154071.95 | UNDATED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 | MARINE PROJECTS | 1 | NAKHEEL PJSC | COMMUNITYCORP LLC | PALM JUMEIRAH | VAN OORD MIDDLE EAST LIMITED (DUBAI BRANCH) | DMS 147906 | DESIGN & BUILD CONTRACT FOR BEACH MAINTENANCE WORKS AT PALM JUMEIRAH | 2022-09-06 | 2022-09-15 | 2023-09-29 | 2023-12-31 | CONTRACTOR | DEFECTS NOTIFICATION PERIOD | 116726996.19 | 119284.72 | 116846280.91 | YES | 5842314.0455 | 122688594.9555 | - | 12 | 2025-04-09 | FINAL | 2025-05-02 | CERTIFIED | 2444987.13 | 2567236.4865 | BANK GUARANTEE | BNP PARIBAS | 06685IGD2200438 | 11672699.62 | END OF DLP | BANK GUARANTEE | BNP PARIBAS | 06685IGD2200434 | 8151662.88 | UNTIL NOTIFIED | BANK GUARANTEE | BNP PARIBAS | 06685IGD2200434 | 8151662.88 | UNTIL NOTIFIED | VAN OORD MIDDLE EAST LTD | ORIENT INSURANCE PJSC | P/01/4012/2022/93 | 124000000 | 2023-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
3 | MARINE PROJECTS | 2 | NAKHEEL PJSC | COMMUNITYCORP LLC | PALM JUMEIRAH | HALCROW INTERNATIONAL PARTNERSHIP (DUBAI BRANCH) | DMS 148942 | DESIGN REVIEW AND SUPERVISION SERVICES OF BEACH MAINTENANCE WORKS | 2022-10-17 | 2024-09-15 | 2023-10-29 | 2023-12-31 | CONSULTANT | CLOSE OUT | 2026426 | 0 | 2026426 | YES | 101321.3 | 2127747.3 | CLOSE OUT IN PROCESS. | 12 | 2025-04-11 | INTERIM | 2025-05-11 | CERTIFIED | 96115.38 | 100921.149 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | CH2M HILL INTERNATIONAL, LTD. - DUBAI BRANCH (CHIL-DUBAI) | EMIRATES INSURANCE | 906/1165/90/21/00005/02 | 10000000 | 2024-07-01
4 | MARINE INSPECTIONS | 2 | NAKHEEL PJSC | DUBAI ISLANDS LLC | DUBAI ISLANDS | WAAGNER BIRO BRIDGE GULF LLC | 3001-2022-0509 | COMPREHENSIVE CLEANING OF MARINE WASHOUT | 2022-11-23 | 2022-12-05 | 2023-11-04 | 2024-02-25 | CONTRACTOR | CLOSED | 2650000 | 1180482 | 3830482 | YES | 191524.1 | 4022006.1 | CONTRACT EXPIRED. FINAL PAYMENT IN PROCESS. | 13 | 2024-03-18 | FINAL | 2024-05-01 | CERTIFIED | 1180482 | 1239506.1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5 | MARINE PROJECTS | 3 | NAKHEEL PJSC | DUBAI ISLANDS LLC | DUBAI ISLANDS | MOTT MACDONALD LTD. (DUBAI BRANCH) | DMS 148857-1 | MARINE CONSULTANCY SERVICES FOR DUBAI ISLANDS A to E | 2023-06-02 | 2023-02-17 | 2023-12-10 | 2023-12-10 | CONSULTANT | ACTIVE | 2203598 | 673211 | 2876809 | YES | 143840.45 | 3020649.45 | - | 10 | 2024-08-01 | INTERIM | 2024-08-31 | CERTIFIED | 636580.46 | 668409.483 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | MOTT MACDONALD LIMITED | EMIRATES INSURANCE | 908/1165/90/20/00015/03 | 10000000 | 2024-06-30
6 | MARINE PROJECTS | 4 | NAKHEEL PJSC | DUBAI ISLANDS LLC | DUBAI ISLANDS | BUREAU VERITAS (DUBAI BRANCH) | 3082-2023-0076 | WATER QUALITY TESTING FOR BLUE FLAG CERTIFICATION OF BEACHES | 2023-07-13 | 2023-06-01 | 2024-05-31 | 2024-05-31 | CONTRACTOR | TERMINATED | 10050 | 0 | 10050 | YES | 502.5 | 10552.5 | - | 5 | 2024-06-07 | INTERIM | ASAP | CERTIFIED | 650 | 682.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
7 | MARINE PROJECTS | 5 | NAKHEEL PJSC | NAKHEEL PJSC | NAKHEEL WATERFRONT PROJECTS | ENVIRO CARE FZE | DMS 149323 | CONSULTANCY SERVICES FOR BLUE FLAG CERTIFICATION OF BEACHES IN CONNECTION WITH PALM JUMEIRAH, DUBAI ISLANDS AND DUBAI WATERFRONT | 2023-07-20 | 2023-07-20 | 2023-12-19 | 2023-12-19 | CONSULTANT | CLOSED | 30000 | 0 | 30000 | NO | 0 | 30000 | CONTRACT IS CLOSED (PO# 3026-2023-0005) | 2 | 2023-10-05 | FINAL | ASAP | CERTIFIED | 6000 | 6000 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
8 | MARINE PROJECTS | 6 | NAKHEEL PJSC | THE WORLD LLC | THE WORLD ISLANDS AND BORROW AREA | HYDROQUAL ASA | DMS 149250 | CONSULTANCY AGREEMENT FOR ENVIRONMENTAL IMPACT ASSESSMENT SERVICES | 2023-08-31 | 2023-08-31 | 2024-06-15 | 2024-06-15 | CONSULTANT | ACTIVE | 1890100 | 0 | 1890100 | YES | 94505 | 1984605 | - | 4 | 2024-11-07 | INTERIM | 2024-12-22 | CERTIFIED | 153960 | 161658 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | HYDROQUAL ASA | ORIENT INSURANCE PJSC | P/01/6023/2023/156 | 3672500 | 2024-05-31
9 | MARINE PROJECTS | 7 | NAKHEEL PJSC | DUBAI ISLANDS LLC | DUBAI ISLANDS | BUREAU VERITAS (DUBAI BRANCH) | 3082-2023-0100 | WATER QUALITY TESTING FOR BLUE FLAG CERTIFICATION OF BEACHES | 2023-09-11 | 2023-09-11 | - | - | CONTRACTOR | TERMINATED | 20160 | 0 | 20160 | YES | 1008 | 21168 | - | 5 | 2024-06-07 | INTERIM | ASAP | CERTIFIED | 1920 | 2016 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
10 | MARINE PROJECTS | 8 | NAKHEEL PJSC | DUBAI WATERFRONT LLC | DUBAI WATERFRONT | DOME INTERNATIONAL SAFETY AND ENVIRONMENTAL CONSULTANTS | DMS 149349 | CONSULTANCY AGREEMENT FOR ENVIRONMENTAL IMPACT ASSESSMENT SERVICES | 2023-11-23 | - | - | - | CONSULTANT | ACTIVE | 821600 | 0 | 821600 | YES | 41080 | 862680 | - | 2 | 2024-02-09 | INTERIM | 2024-03-22 | CERTIFIED | 451880 | 474474 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | DOME INTERNATIONAL SAFETY AND ENVIRONMENTAL CONSULTANTS | ABU DHABI NATIONAL INSURANCE COMPANY | H155130047709-R06 | 18350000 | 2024-11-30
11 | MARINE PROJECTS | 9 | NAKHEEL PJSC | NAKHEEL PJSC | NAKHEEL WATERFRONT PROJECTS | ENVIRO CARE FZE | 3001-2023-0572 | BLUE FLAG CERTIFICATION FOR ALL NAKHEEL BEACHES | 2023-12-20 | 2023-12-20 | 2025-12-19 | 2025-12-19 | CONSULTANT | ACTIVE | 154600 | 0 | 154600 | YES | 7730 | 162330 | - | 8 | 2024-12-12 | INTERIM | ASAP | CERTIFIED | 2660 | 2660 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
12 | MARINE PROJECTS | 10 | NAKHEEL PJSC | COMMUNITYCORP LLC | PALM JUMEIRAH | IMDAAD LLC | 3203-2024-0059 | PALM JUMEIRAH BEACHES AND SURFACE WATER CLEANING (AGREEMENT 94478) | 2024-02-21 | 2024-03-01 | 2027-02-28 | 2027-02-28 | CONTRACTOR | ACTIVE | 8850000 | 0 | 8850000 | YES | 442500 | 9292500 | - | 3 | 2024-12-17 | INTERIM | 2025-02-04 | PENDING | 231249.99 | 242812.4895 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
13 | MARINE INSPECTIONS | 3 | NAKHEEL PJSC | DUBAI ISLANDS LLC | DUBAI ISLANDS | IFM FACILITIES MANAGEMENT LLC | 3082-2024-0024 | COMPREHENSIVE CLEANING OF MARINE WASHOUT ALONG THE MARINE EDGES OF DUBAI ISLANDS A, B, C, D AND E FOR 3 YEARS | 2024-02-22 | 2024-04-01 | 2027-03-31 | 2027-03-31 | CONTRACTOR | ACTIVE | 1611872.2 | 0 | 1611872.2 | YES | 80593.61 | 1692465.81 | - | 4 | 2025-01-16 | INTERIM | 2025-05-17 | CERTIFIED | 44774.23 | 47012.9415 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
14 | MARINE PROJECTS | 11 | NAKHEEL PJSC | NAKHEEL PJSC | NAKHEEL WATERFRONT PROJECTS | WAFA BIOLOGICAL LABORATORY LLC | 3001-2024-0166 | WATER QUALITY TESTING IN NAKHEEL WATERFRONT PROJECTS | 2024-03-04 | 2024-03-05 | 2027-03-04 | 2027-03-04 | CONTRACTOR | ACTIVE | 179340 | 0 | 179340 | YES | 8967 | 188307 | - | 5 | 2025-02-20 | INTERIM | ASAP | CERTIFIED | 6831 | 7172.55 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
15 | MARINE PROJECTS | 12 | NAKHEEL PJSC | DUBAI ISLANDS LLC | DUBAI ISLANDS | DOME INTERNATIONAL SAFETY AND ENVIRONMENTAL CONSULTANTS | DMS 149600 | CONSULTANCY AGREEMENT FOR ENVIRONMENTAL IMPACT ASSESSMENT (EIA) FOR OFFSHORE BORROW AREAS 13 & 14 | 2024-03-06 | 2024-03-06 | 2024-05-21 | 2024-05-21 | CONSULTANT | ACTIVE | 548380 | 0 | 548380 | YES | 27419 | 575799 | - | 1 | 2024-07-23 | INTERIM | 2024-08-25 | CERTIFIED | 493542 | 518219.1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | DOME INTERNATIONAL SAFETY AND ENVIRONMENTAL CONSULTANTS | ABU DHABI NATIONAL INSURANCE COMPANY | H155130047709-R06 | 18350000 | 2024-11-30
16 | MARINE INSPECTIONS | 4 | NAKHEEL PJSC | NAKHEEL PJSC | NAKHEEL WATERFRONT PROJECTS | NORTH WEST MARINE EQUIPMENT TRADING LLC | 3001-2024-0207 | SUPPLY & INSTALLATION OF NAVIGATION BUOYS AT ALL NAKHEEL WATERFRONT PROJECTS | 2024-03-21 | - | - | - | CONTRACTOR | ACTIVE | 5452593 | 0 | 5452593 | YES | 272629.65 | 5725222.65 | - AGREEMENT 96435 - CONTRACT NOT YET SIGNED. 2nd SIGNATORY UNDECIDED. THE MAINTENANCE PERIOD WILL START AFTER COMPLETION OF INSTALLATION OF ALL BUOYS. | 1 | 2024-09-17 | INTERIM | 2024-11-05 | CERTIFIED | 3936989.39 | 4133838.8595 | BANK GUARANTEE | COMMERCIAL BANK OF DUBAI | OLG2401469-17 | 234728 | 2027-06-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
17 | MARINE INSPECTIONS | 5 | NAKHEEL PJSC | NAKHEEL PJSC | NAKHEEL MARINE ENGINEERING | ROOH AL MASHRIQ FASHION | 3026-2023-0004 | SUPPLY OF UNIFORM FOR NAKHEEL MARINE ENGINEERING | - | - | - | - | SUPPLIER | CLOSED | 39370 | 0 | 39370 | YES | 1968.5 | 41338.5 | AWAITING RECEIPT OF FINAL INVOICE | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
18 | MARINE PROJECTS | 13 | DUBAI HOLDING REAL ESTATE | THE PALM JEBEL ALI CO. LLC | PALM JEBEL ALI | JAN DE NUL DREDGING LTD. (DUBAI BRANCH) | DMS 148763 | MARINE WORKS INCLUDING DREDGING, LAND RECLAMATION AND BEACH PROFILING | 2024-08-23 | 2024-09-05 | 2026-11-08 | 2026-11-08 | CONTRACTOR | ACTIVE | 810529166.67 | 108283114.76 | 918812281.43 | YES | 45940614.0715 | 964752895.5015 | - | 9 | 2025-05-21 | INTERIM | 2025-07-14 | CERTIFIED | 30214778.63 | 31725517.5615 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
19 | MARINE INSPECTIONS | 6 | NAKHEEL PJSC | NAKHEEL PJSC | NAKHEEL WATERFRONT PROJECTS | INCHCAPE SHIPPING SERVICES (DUBAI) LLC | 3026-2024-0001 | SUPPLY OF REMOTELY OPERATED VEHICLES (ROV'S) | 2024-02-15 | 2024-02-15 | 2024-03-14 | 2024-03-14 | SUPPLIER | CLOSED | 662142 | 0 | 662142 | YES | 33107.1 | 695249.1 | - | 1 | 2024-03-28 | FINAL | 2024-04-27 | CERTIFIED | 662142 | 695249.1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
20 | MARINE PROJECTS | 14 | NAKHEEL PJSC | THE WORLD LLC | THE WORLD ISLANDS | PLC MARINE TRANSPORT LLC | 3116-2024-0006 | URGENT EMERGENCY WORKS IN THE WORLD - REMOVAL OF CAUSEWAY, CONCRETE DEMOLITION AND DISPOSAL | 2024-02-07 | 2024-02-06 | 2024-02-29 | 2024-02-29 | CONTRACTOR | CLOSED | 794178 | 0 | 794178 | YES | 39708.9 | 833886.9 | - | 1 | 2024-02-27 | FINAL | IMMEDIATE | CERTIFIED | 794178 | 833886.9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
21 | MARINE PROJECTS | 15 | DUBAI HOLDING REAL ESTATE | THE PALM JEBEL ALI CO. LLC | PALM JEBEL ALI | HALCROW INTERNATIONAL PARTNERSHIP (DUBAI BRANCH) | DMS 149746 | CONSTRUCTION SITE SUPERVISION SERVICES FOR MARINE AND GROUND IMPROVEMENT WORKS | 2024-08-21 | 2024-07-12 | 2028-01-11 | 2028-01-11 | CONSULTANT | ACTIVE | 9992685 | 0 | 9992685 | YES | 499634.25 | 10492319.25 | - | 3 | 2025-01-24 | INTERIM | 2025-02-21 | CERTIFIED | 378676.98 | 397610.829 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
22 | MARINE PROJECTS | 16 | NAKHEEL PJSC | THE PALM JEBEL ALI CO. LLC | PALM JEBEL ALI | BUREAU VERITAS (DUBAI BRANCH) | 3051-2023-0077 | WATER QUALITY TESTING FOR BLUE FLAG CERTIFICATION OF BEACHES | 2023-12-15 | 2023-12-15 | - | - | CONTRACTOR | CLOSED | 28350 | 0 | 28350 | YES | 1417.5 | 29767.5 | - | 1 | 2023-12-15 | FINAL | 2024-01-14 | CERTIFIED | 28350 | 29767.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
23 | MARINE PROJECTS | 17 | NAKHEEL PJSC | DUBAI ISLANDS LLC | DUBAI ISLANDS | BUREAU VERITAS (DUBAI BRANCH) | 3082-2023-0099 | WATER QUALITY TESTING WORKS REQUIRED TO SUPPORT THE PREPARATION OF A WATER QUALITY REPORT BY M/S. DOME | 2023-09-11 | 2023-09-11 | - | - | CONTRACTOR | CLOSED | 55450 | 0 | 55450 | YES | 2772.5 | 58222.5 | - | 1 | 2023-09-12 | FINAL | ASAP | CERTIFIED | 55450 | 58222.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
24 | MARINE PROJECTS | 18 | DUBAI HOLDING REAL ESTATE | THE PALM JEBEL ALI CO. LLC | PALM JEBEL ALI | HALCROW INTERNATIONAL PARTNERSHIP (DUBAI BRANCH) | DMS 149074 | MARINE IMPACT STUDY CONSULTANCY SERVICES FOR THE PALM JEBEL ALI - FRAMEWORK AGREEMENT | 2024-01-29 | 2024-01-29 | 2027-01-28 | 2027-01-08 | CONSULTANT | ACTIVE | 0 | 0 | 0 | YES | 0 | 0 | - | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
25 | MARINE INSPECTIONS | 7 | DUBAI HOLDING REAL ESTATE | NAKHEEL PJSC | NAKHEEL WATERFRONT PROJECTS | DUBAI MARITIME CITY AUTHORITY | DMCA-01 | RENEWAL OF SAFE ATONS CERTIFICATE FOR ALL DUBAI HOLDING PROJECTS | - | 2025-01-01 | 2025-12-31 | 2025-12-31 | AUTHORITY | ACTIVE | 400080 | 0 | 400080 | NO | 0 | 400080 | NO CONTRACT AGREEMENT IS AVAILABLE FOR THIS. IT IS A YEARLY FEE PAID TO DMCA AUTHORITY. | 1 | 2025-01-03 | FINAL | 2025-02-17 | CERTIFIED | 400080 | 400080 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
26 | MARINE INSPECTIONS | 8 | DUBAI HOLDING REAL ESTATE | THE PALM JEBEL ALI CO. LLC | PALM JEBEL ALI | IMDAAD LLC | DMS 149832 | PALM JEBEL ALI BEACH CLEANING WORKS | TBA | TBA | TBA | TBA | CONTRACTOR | ACTIVE | 795756 | 0 | 795756 | YES | 39787.8 | 835543.8 | CONTRACT TO BE FINALIZED BY P&C | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
27 | MARINE PROJECTS | 19 | DUBAI HOLDING REAL ESTATE | THE POINTE LLC | PALM JUMEIRAH | VAN OORD MIDDLE EAST LIMITED (DUBAI BRANCH) | DMS 149853 | THE POINTE REDEVELOPMENT FOR THE DESIGN & BUILD BEACHES | 2025-04-07 | 2025-05-07 | 2025-12-02 | 2025-12-02 | CONTRACTOR | ACTIVE | 17245634 | 0 | 17245634 | YES | 862281.7 | 18107915.7 | - | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LR | [14 empty] | 986799966.06 | 110256092.48 | 1097056058.54 |  | 54831298.927 | 1151887357.467 | [6 empty] | 42250964.19 | 44343075.3995 |  |  |  | 12061499.57 |  |  |  |  | 8151662.88 |  |  |  |  | 8151662.88 |  |  |  |  | 124000000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 60372500
Formulas:
REVISED COMPLETION DATE = IF([COMPLETION DATE]="","",[COMPLETION DATE])
REVISED COMPLETION DATE = [COMPLETION DATE]
DATED = IFERROR(IF([LATEST CERTIFIED PC #]=0,"N/A",VLOOKUP(MAX('[1]DMS 147714'!A:A), '[1]DMS 147714'!A:I, 2, FALSE)),"N/A")
DATED = IFERROR(IF([LATEST CERTIFIED PC #]=0,"N/A",VLOOKUP(MAX('[1]3001-2022-0509'!A:A), '[1]3001-2022-0509'!A:I, 2, FALSE)),"N/A")
DUE DATE = IFERROR(IF([LATEST CERTIFIED PC #]=0,"N/A",VLOOKUP(MAX('[1]DMS 147714'!A:A), '[1]DMS 147714'!A:I, 4, FALSE)),"N/A")
DUE DATE = IFERROR(IF([LATEST CERTIFIED PC #]=0,"N/A",VLOOKUP(MAX('[1]3001-2022-0509'!A:A), '[1]3001-2022-0509'!A:I, 4, FALSE)),"N/A")
COMPLETION DATE = [COMMENCEMENT DATE]+77-1